## Main
Scrum Project
Product | DrugTime
Active versions | v1.0
Team |  |  | Product Owner | Nguyen Van Nguyen
Scrum Master | Nguyen Ngoc Phuc |  | Other Stakeholders | B.Eng. Nguyen Trong Giap
Developers | Nguyen Ngoc Phuc
Nguyen Van Nguyen
Nguyen Quang Bao
Nguyen Tan Duc
Dang Ngo Ngoc Viet
Projects | [5 empty] | Sprint Plan
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
1 | DrugTime MVP (Capstone Project 1) | 2026-09-10 | 2026-12-06 | In Progress | Implementation only | 1 | 2026-09-14 | 2026-09-27 | Not started | 250
2 | DrugTime - Full Project (Initiation to Capstone Defense) | 2026-09-10 | 2026-12-26 | In Progress |  | 2 | 2026-09-28 | 2026-10-11 | Not started | 250
[6 empty] | 3 | 2026-10-12 | 2026-10-25 | Not started | 250
[6 empty] | 4 | 2026-10-26 | 2026-11-08 | Not started | 250
[6 empty] | 5 | 2026-11-09 | 2026-11-22 | Not started | 250
[6 empty] | 6 | 2026-11-23 | 2026-12-06 | Not started | 250
Formulas:
End = [Start]+13
Start = [End, row above]+1

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register / Login | Patient | Register and log into my account | I can securely access the app | - POST /auth/register + /auth/login return 200/401 correctly - Password hashed, session token issued - Mobile UI: form validation, error states |  | 1 | Not started | User Story | 1 | 1 | 25
PB02 | Purpose-separated consent | Patient | Complete consent separately for each data-processing purpose | My data is only used for what I explicitly agreed to (PDPL 2025) | - DB table `consents` stores purpose, granted_at - UI: one toggle per purpose, no 'Accept All' button - Backend blocks data action if purpose not consented - Revoking one purpose does not affect consent already granted for other purposes |  | 1 | Not started | User Story | 1 | 1 | 25
PB03 | Manage health profile | Patient | Create and edit my health profile | The system has accurate info to base reminders and warnings on | - CRUD /profile endpoint - Mobile form with validation |  | 1 | Not started | User Story | 1 | 2 | 20
PB04 | Manage medication catalog | Admin | Add, edit, and remove medications in the catalog | Patients can match their medications against an accurate list | - Admin dashboard CRUD table - Search/filter by name - Soft-delete only: entries referenced by existing patient history cannot be hard-deleted (avoid breaking historical records) |  | 1 | Not started | User Story | 1 | 2 | 20
PB05 | Manage interaction catalog | Admin | Add, edit, and remove drug-drug/drug-food interaction records | Interaction warnings shown to patients are accurate | - Admin dashboard CRUD table - Linked to medication catalog by ID - Soft-delete only: entries referenced by existing patient history cannot be hard-deleted (avoid breaking historical records) |  | 1 | Not started | User Story | 1 | 2 | 20
PB06 | Synchronize catalog from external sources | Admin | Trigger a periodic sync job pulling from the Vietnamese Drug Regulatory Data Source | The catalog stays current without manual re-entry | - RQ scheduled job runs weekly/monthly - Sync log stored with timestamp + record count | Task split: research+build in S1, logging+testing in S2 | 1 | Not started | User Story | 1 | 1 | 55
PB07 | CI/CD pipeline & environment setup | Team | Have automated build/test/deploy pipeline | Every sprint ships without manual deployment steps | - GitHub Actions runs test+lint on PR - Auto-deploy to Oracle Cloud VM on merge to main |  | 1 | Not started | Technical Task | 1 | 1 | 30
PB08 | Database schema design & migrations | Team | Have a versioned DB schema | All modules share a consistent, evolvable data model | - ERD reviewed & approved - Migration scripts run cleanly on empty DB |  | 1 | Not started | Technical Task | 1 | 1 | 35
PB09 | Patient-Family linking data model | Team | Have a many-to-many linking table between patients and family members | Sprint 3 features (linking, alerts) have a schema to build on | - Table `patient_family_links` with status/consent fields - Unit tested for many-to-many |  | 1 | Not started | Technical Task | 1 | 2 | 20
PB10 | Add medication (manual input) | Patient | Add a medication by entering its name, dose, and schedule manually | I can start tracking a medication without scanning | - POST /medications validates required fields - Mobile form: name, dose, time, frequency |  | 1 | Not started | User Story | 1 | 2 | 25
PB11 | Manage medication schedule | Patient | Edit the time, dose, and frequency of a medication | My schedule stays accurate as prescriptions change | - PUT /medications/{id}/schedule - UI supports edit/delete of a schedule entry |  | 1 | Not started | User Story | 1 | 2 | 20
PB12 | Receive reminder | Patient | Get a local notification at each scheduled dose time | I don't forget to take my medication | - Local notification fires within 2s of scheduled time (NFR05) - Works offline (on-device scheduling) - No reminder sent if the dose was already confirmed before the scheduled time - Correct handling when multiple medications share the same reminder time (all shown, none dropped) |  | 1 | Not started | User Story | 1 | 2 | 40
PB13 | Confirm dose intake | Patient | Tap a button to confirm I took a dose | My adherence is tracked accurately | - Button confirmation writes to adherence log - Confirmed state reflected in reminder UI immediately |  | 1 | Not started | User Story | 1 | 2 | 20
PB14 | View adherence history | Patient | See a log of doses taken/missed by day and by medication | I can track my own consistency | - GET /adherence returns list grouped by date+medication - Mobile screen renders calendar/list view |  | 1 | Not started | User Story | 1 | 3 | 20
PB15 | Link family member | Patient | Generate a QR code or referral code to link a family member | They can monitor my adherence | - POST /links/generate returns QR payload + code - Code expires after 24h |  | 2 | Not started | User Story | 1 | 3 | 20
PB16 | Confirm data-sharing consent on linking | Patient | Confirm what data is shared when a family member links | Sharing stays within the purpose I explicitly agreed to | - Linking flow blocked until consent confirmed - Consent record linked to the specific family member ID |  | 1 | Not started | User Story | 1 | 3 | 15
PB17 | Remove linked family member | Patient | Remove a previously linked family member | I can revoke their access at any time | - DELETE /links/{id} removes access immediately - Family member's app reflects the change on next sync |  | 2 | Not started | User Story | 1 | 3 | 10
PB18 | Revoke data-sharing permission | Patient | Revoke data-sharing without fully removing the link | I can pause sharing without ending the relationship | - PATCH /links/{id}/consent sets shared=false - Family member's Drug Safety Lookup access blocked immediately |  | 2 | Not started | User Story | 1 | 3 | 10
PB19 | Link to patient account | Family Member | Scan a QR code or enter a referral code to link to a patient | I can start monitoring them | - POST /links/redeem validates code, creates link - No cap on number of linked patients |  | 2 | Not started | User Story | 1 | 3 | 20
PB20 | Receive missed-dose alert | Family Member | Get a real-time alert when a linked patient misses a dose | I can check on them promptly | - Push notification within 2s of missed-dose detection - Alert names the patient explicitly - No missed-dose alert sent if the patient confirms the dose just before the detection job runs (avoid false alert to Family Member) |  | 1 | Not started | User Story | 1 | 3 | 40
PB21 | View adherence history | Family Member | View basic adherence history of a linked patient | I can understand their consistency over time | - GET /adherence?patient_id= scoped by active consent - Blocked if consent revoked |  | 1 | Not started | User Story | 1 | 3 | 15
PB22 | Manage multiple linked patients | Family Member | Switch between multiple linked patients in the app | I can monitor more than one family member | - Patient-switcher UI component - Data scoped correctly per selected patient (no data leak) |  | 2 | Not started | User Story | 1 | 3 | 35
PB23 | Look up medication information | Patient | Search for and view details of a medication | I understand what I'm taking | - GET /medications/search?q= - Result includes dosage form, active ingredient |  | 1 | Not started | User Story | 1 | 4 | 20
PB24 | View drug-drug interaction warning | Patient | See a warning if two of my medications interact | I'm alerted to a potential safety risk | - Warning screen triggered on medication add if conflict found - Mandatory disclaimer text always shown (NFR03) - Interaction-detection logic validated against a standardized drug-drug interaction test-case set (must cover true-positive pairs, true-negative/no-interaction pairs, and known edge cases), not just UI text presence - Test case set reviewed/approved by mentor before Sprint 4 acceptance - Multiple simultaneous interactions: all conflicting pairs are listed, not only the first match found - UI distinguishes 3 result states, each with a distinct, clearly worded message: (1) Interaction found -> warning shown; (2) Not found within checked data -> neutral wording (e.g. 'no known interaction in current database'), never phrased as a guarantee of safety; (3) Insufficient data (e.g. medication/food not in catalog) -> explicit 'cannot verify, please consult a pharmacist' message, not silently treated as 'no interaction' |  | 1 | Not started | User Story | 1 | 4 | 30
PB25 | View drug-food interaction warning | Patient | See a warning if a medication interacts with a food | I can avoid risky food combinations | - Warning shown in AI meal suggestion + standalone lookup - Mandatory disclaimer text always shown - Detection logic validated against the same standardized test-case approach as PB24 (true-positive/true-negative food-drug pairs) - Multiple conflicting foods in one meal suggestion are all surfaced, not only the first match found - UI distinguishes 3 result states, each with a distinct, clearly worded message: (1) Interaction found -> warning shown; (2) Not found within checked data -> neutral wording (e.g. 'no known interaction in current database'), never phrased as a guarantee of safety; (3) Insufficient data (e.g. medication/food not in catalog) -> explicit 'cannot verify, please consult a pharmacist' message, not silently treated as 'no interaction' |  | 1 | Not started | User Story | 1 | 4 | 25
PB26 | Look up medication info of linked patient | Family Member | Search medication info for a linked patient | I can help them understand their treatment | - Same as Patient lookup, scoped by consent+patient_id - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 4 | 15
PB27 | View drug-drug interaction of linked patient | Family Member | View drug-drug warnings for a linked patient | I can help spot safety risks | - Reuses Patient interaction logic, scoped by consent - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 4 | 20
PB28 | View drug-food interaction of linked patient | Family Member | View drug-food warnings for a linked patient | I can help with meal planning for them | - Reuses Patient interaction logic, scoped by consent - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 4 | 20
PB29 | iOS build/signing pipeline setup | Team | Have a working iOS build and TestFlight/Ad Hoc signing pipeline | The MVP can ship on both Android and iOS as committed | - Mac build produces signed .ipa - Installable via TestFlight or Ad Hoc |  | 1 | Not started | Technical Task | 1 | 1 | 55
PB30 | Cross-device testing (Android + iOS) | Team | Run core flows on real Android and iOS devices | We catch platform-specific bugs before later sprints | - Test checklist covers onboarding, reminder, confirmation on both OS - Defects logged in tracker |  | 1 | Not started | Technical Task | 1 | 4 | 25
PB31 | Scan blister pack | Patient | Scan a medication blister pack with the camera | I can add a medication faster than typing it | - On-device ML Kit recognition, no image leaves device - Falls back to manual search if no match (Risk R-01) - Recognition-confidence threshold defined; below it, auto-fallback to manual search instead of showing a possibly-wrong match |  | 1 | Not started | User Story | 1 | 5 | 80
PB32 | Confirm medication | Patient | Manually verify a scanned or entered medication before saving | Incorrect matches don't silently enter my schedule | - Confirmation step is mandatory, cannot be skipped - Shows matched catalog entry for review |  | 1 | Not started | User Story | 1 | 5 | 15
PB33 | Switch to Simple Mode UI | Patient | Switch to a high-contrast, single-button interface | I can use the app easily despite low tech literacy | - Toggle in settings persists across sessions - Simple Mode screen shows only next dose + 1 confirm button |  | 2 | Not started | User Story | 1 | 5 | 30
PB34 | Withdraw consent / request data deletion | Patient | Withdraw consent or request my data be deleted | I retain control over my personal data (PDPL 2025) | - Settings action triggers deletion request record - Confirmation shown to patient immediately |  | 1 | Not started | User Story | 1 | 5 | 20
PB35 | Process data deletion / consent withdrawal requests | Admin | View and process pending deletion/withdrawal requests | Compliance obligations are met within a defined SLA | - Admin queue lists pending requests - Marking 'processed' triggers actual data deletion job |  | 1 | Not started | User Story | 1 | 5 | 25
PB36 | View sensitive-data access log | Admin | View a log of who accessed a patient's sensitive health data | The system is auditable under DPIA obligations | - Log entry created on every Family Member/Admin data view - Filterable by patient, date, actor |  | 2 | Not started | User Story | 1 | 5 | 20
PB37 | View AI meal suggestion with explanation | Patient | See a suggested meal based on my current medications, with a brief explanation | I can make safer dietary choices | - LLM API call returns suggestion + explanation within acceptable latency - Medical disclaimer always shown (R-07) - Meal suggestion distinguishes the same 3 states for food-drug conflict checks (found / not found in checked data / insufficient data), never silently defaulting to 'safe' |  | 1 | Not started | User Story | 1 | 6 | 45
PB39 | View AI meal suggestion for linked patient | Family Member | View the AI meal suggestion generated for a linked patient | I can help plan meals for them | - Reuses Patient meal-suggestion endpoint, scoped by consent |  | 2 | Not started | User Story | 1 | 6 | 10
PB41 | Conduct DPIA for new sensitive-data flows | Admin | Complete a Data Protection Impact Assessment before go-live | The platform is compliant with the 2025 PDPL before launch | - DPIA document completed and reviewed with mentor - Signed off before Sprint 6 ends | Task split: preliminary draft in S1, update+review+signoff in S6 | 1 | Not started | User Story | 1 | 6 | 40
PB42 | Review PDPL 2025 / Decree 356 compliance | Admin | Review the full platform against PDPL 2025 and Decree 356 requirements | No compliance gap remains before final submission | - Compliance checklist completed - Any gap logged and resolved before Final Submission |  | 1 | Not started | User Story | 1 | 6 | 25
PB43 | Full-system bug-fixing (Android + iOS) | Team | Fix defects found during end-to-end testing | The final submission is stable on both platforms | - All Sprint 1-5 features retested end-to-end - Critical/High bugs resolved before Integration phase |  | 1 | Not started | Technical Task | 1 | 6 | 70
[11 empty] | Total | 1130
Note on M7: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.01 | PB08 | Design ERD (patient, medication, consent, family_link, catalog tables,…) | Phuc, Nguyen | Not started | 14 | 0 | 14 | 0 | -14
1.02 | PB08 | Write Supabase migration scripts | Phuc, Nguyen | Not started | 10 | 0 | 10 | 0 | -10
1.03 | PB08 | Review & test migrations on clean DB | Viet, Bao, Duc | Not started | 10 | 0 | 10 | 0 | -10
1.04 | PB07 | Setup GitHub Actions (lint + test on PR) | Bao | Not started | 10 | 0 | 10 | 0 | -10
1.05 | PB07 | Setup auto-deploy to Oracle Cloud VM | Duc | Not started | 10 | 0 | 10 | 0 | -10
1.06 | PB07 | Configure Caddy for automatic HTTPS | Viet | Not started | 7 | 0 | 7 | 0 | -7
1.07 | PB29 | Confirm Mac access + configure free Apple ID in Xcode | Duc, Phuc | Not started | 7 | 0 | 7 | 0 | -7
1.08 | PB29 | Configure Xcode project + automatic signing | Duc, Phuc | Not started | 17 | 0 | 17 | 0 | -17
1.09 | PB29 | Test: build & run app on real device via Xcode (USB/Wi-Fi debugging) | Duc, Phuc | Not started | 17 | 0 | 17 | 0 | -17
1.10 | PB01 | Backend: Supabase Auth integration (register/login API) | Nguyen, Bao | Not started | 7 | 0 | 7 | 0 | -7
1.11 | PB01 | Mobile: Register/Login UI screens | Bao, Duc | Not started | 10 | 0 | 10 | 0 | -10
1.12 | PB01 | Mobile-Backend integration + error handling | Bao, Duc | Not started | 5 | 0 | 5 | 0 | -5
1.13 | PB01 | Test: unit + widget test | Bao, Duc | Not started | 3 | 0 | 3 | 0 | -3
1.14 | PB02 | Backend: consents table + grant/revoke API per purpose | Viet, Phuc | Not started | 10 | 0 | 10 | 0 | -10
1.15 | PB02 | Mobile: consent UI (per-purpose toggles, no 'Accept All') | Viet, Phuc | Not started | 9 | 0 | 9 | 0 | -9
1.16 | PB02 | Test: consent flow end-to-end | Viet, Phuc | Not started | 5 | 0 | 5 | 0 | -5
1.17 | PB06 | Research/parse Vietnamese Drug Regulatory Data Source structure | All team member | Not started | 14 | 0 | 14 | 0 | -14
1.18 | PB06 | Build RQ scheduled sync job | All team member | Not started | 21 | 0 | 21 | 0 | -21
1.19 | PB41 | Draft preliminary DPIA (based on planned sensitive-data flows) | Phuc, Nguyen | Not started | 10 | 0 | 10 | 0 | -10
|  |  |  | Total | 196 | 0 | 196 | 0 | -196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2.01 | PB10 | Backend: Add medication API + validation | Nguyen, Viet | Not started | 10 | 0 | 10 | 0 | -10
2.02 | PB10 | Mobile: Add medication form UI | Bao, Duc | Not started | 10 | 0 | 10 | 0 | -10
2.03 | PB10 | Test: unit + widget test (add medication) | Bao, Duc | Not started | 6 | 0 | 6 | 0 | -6
2.04 | PB11 | Backend: medication schedule CRUD API | Nguyen, Phuc | Not started | 7 | 0 | 7 | 0 | -7
2.05 | PB11 | Mobile: schedule edit UI | Bao, Duc | Not started | 7 | 0 | 7 | 0 | -7
2.06 | PB11 | Test: schedule CRUD | Duc, Viet | Not started | 7 | 0 | 7 | 0 | -7
2.07 | PB12 | Mobile: local notification scheduling (flutter_local_notifications) | Bao, Duc | Not started | 17 | 0 | 17 | 0 | -17
2.08 | PB12 | Mobile: notification edge cases (timezone, multi-dose/day) | Bao, Phuc | Not started | 10 | 0 | 10 | 0 | -10
2.09 | PB12 | Test: verify reminder fires within 2s (NFR05) | Viet, Phuc | Not started | 9 | 0 | 9 | 0 | -9
2.10 | PB13 | Backend: dose confirmation API + adherence log write | Nguyen, Viet | Not started | 8 | 0 | 8 | 0 | -8
2.11 | PB13 | Mobile: confirm button UI + state update | Bao, Duc | Not started | 8 | 0 | 8 | 0 | -8
2.12 | PB13 | Test: confirm dose flow end-to-end | Duc, Nguyen | Not started | 3 | 0 | 3 | 0 | -3
2.13 | PB03 | Backend: health profile CRUD API | Nguyen | Not started | 8 | 0 | 8 | 0 | -8
2.14 | PB03 | Mobile: profile form UI | Nguyen, Bao | Not started | 7 | 0 | 7 | 0 | -7
2.15 | PB03 | Test: profile CRUD | Nguyen | Not started | 3 | 0 | 3 | 0 | -3
2.16 | PB04 | Backend: medication catalog CRUD API | Phuc, Nguyen, Viet | Not started | 8 | 0 | 8 | 0 | -8
2.17 | PB04 | Admin dashboard: catalog table UI (React/Next.js) | Nguyen, Bao | Not started | 10 | 0 | 10 | 0 | -10
2.18 | PB04 | Test: catalog CRUD | Phuc, Duc | Not started | 3 | 0 | 3 | 0 | -3
2.19 | PB05 | Backend: interaction catalog CRUD API | Phuc, Duc | Not started | 8 | 0 | 8 | 0 | -8
2.20 | PB05 | Admin dashboard: interaction catalog UI | Phuc, Duc | Not started | 10 | 0 | 10 | 0 | -10
2.21 | PB05 | Test: interaction catalog CRUD | Phuc, Duc | Not started | 3 | 0 | 3 | 0 | -3
2.22 | PB09 | Backend: design & build patient_family_links table | Phuc, Nguyen, Viet | Not started | 10 | 0 | 10 | 0 | -10
2.23 | PB09 | Backend: unit test many-to-many linking logic | Phuc, Nguyen, Viet | Not started | 10 | 0 | 10 | 0 | -10
2.24 | PB06 | Sync logging + error handling | Duc, Viet | Not started | 10 | 0 | 10 | 0 | -10
2.25 | PB06 | Test sync job end-to-end | Duc | Not started | 7 | 0 | 7 | 0 | -7
|  |  |  | Total | 199 | 0 | 199 | 0 | -199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
| Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
3.01 | PB14 | Backend: GET /adherence (group by date/medication) | Phuc, Viet | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.02 | PB14 | Mobile: adherence calendar/list UI | Bao, Duc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.03 | PB14 | Test: adherence history | Nguyen, Viet | Not started | 3 | 0 | 3 | 0 | -3
3.04 | PB15 | Backend: QR/referral code generation API | Nguyen, Phuc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.05 | PB15 | Mobile: generate & display QR/code UI | Bao, Duc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.06 | PB15 | Test: code generation + 24h expiry | Viet, Phuc | Not started | 6.5 | 0 | 6.5 | 0 | -6.5
3.07 | PB16 | Backend: block linking until consent confirmed | Nguyen, Viet | Not started | 5 | 0 | 5 | 0 | -5
3.08 | PB16 | Mobile: consent confirmation screen during linking | Bao, Nguyen | Not started | 5 | 0 | 5 | 0 | -5
3.09 | PB16 | Test: consent-on-link flow | Phuc, Viet | Not started | 3 | 0 | 3 | 0 | -3
3.10 | PB17 | Backend: DELETE /links/{id} API | Nguyen | Not started | 5 | 0 | 5 | 0 | -5
3.11 | PB17 | Mobile: remove-link UI + confirm dialog | Bao | Not started | 5 | 0 | 5 | 0 | -5
3.12 | PB18 | Backend: PATCH /links/{id}/consent (shared=false) | Viet | Not started | 5 | 0 | 5 | 0 | -5
3.13 | PB18 | Mobile: toggle data-sharing UI | Nguyen | Not started | 5 | 0 | 5 | 0 | -5
3.14 | PB19 | Backend: POST /links/redeem (validate + create link) | Nguyen, Phuc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.15 | PB19 | Mobile: scan QR / enter code UI (Family Member) | Bao, Duc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.16 | PB19 | Test: redeem flow | Viet | Not started | 3 | 0 | 3 | 0 | -3
3.17 | PB20 | Backend: missed-dose detection scheduled job | Phuc, Viet | Not started | 14 | 0 | 14 | 0 | -14
3.18 | PB20 | Backend: alert dispatch logic to Family Member | Nguyen, Viet | Not started | 10.5 | 0 | 10.5 | 0 | -10.5
3.19 | PB20 | Mobile: Family Member alert handling UI | Bao, Duc | Not started | 7 | 0 | 7 | 0 | -7
3.20 | PB20 | Test: alert fires <2s, names patient explicitly | Phuc, Viet | Not started | 7 | 0 | 7 | 0 | -7
3.21 | PB21 | Backend: GET /adherence?patient_id= scoped by consent | Nguyen, Phuc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
3.22 | PB21 | Mobile: Family Member adherence view UI | Bao, Duc | Not started | 5 | 0 | 5 | 0 | -5
3.23 | PB21 | Test: adherence history (Family Member) | Viet | Not started | 3 | 0 | 3 | 0 | -3
3.24 | PB22 | Backend: list linked patients API | Phuc | Not started | 7 | 0 | 7 | 0 | -7
3.25 | PB22 | Mobile: patient-switcher UI component | Bao, Duc | Not started | 17.5 | 0 | 17.5 | 0 | -17.5
3.26 | PB22 | Mobile: scope data correctly per selected patient | Duc, Viet | Not started | 7 | 0 | 7 | 0 | -7
3.27 | PB22 | Test: verify no cross-patient data leak | Phuc, Nguyen | Not started | 3.5 | 0 | 3.5 | 0 | -3.5
|  |  |  | Total | 179.5 | 0 | 179.5 | 0 | -179.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5 | 179.5
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 4 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
4.01 | PB23 | Backend: GET /medications/search API | Nguyen, Viet | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
4.02 | PB23 | Mobile: medication lookup search UI | Bao, Duc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
4.03 | PB23 | Test: medication lookup | Phuc | Not started | 3 | 0 | 3 | 0 | -3
4.04 | PB24 | Backend: drug-drug interaction-check logic | Nguyen, Viet | Not started | 14 | 0 | 14 | 0 | -14
4.05 | PB24 | Mobile: warning screen UI + mandatory disclaimer | Bao, Duc | Not started | 10.5 | 0 | 10.5 | 0 | -10.5
4.06 | PB24 | Test: validate interaction-detection algorithm against standardized test-case set (true/false positives) + verify disclaimer always shown | Phuc, Viet | Not started | 7 | 0 | 7 | 0 | -7
4.07 | PB25 | Backend: drug-food interaction lookup logic | Nguyen, Phuc | Not started | 10.5 | 0 | 10.5 | 0 | -10.5
4.08 | PB25 | Mobile: food-warning screen UI (reuse) | Bao, Duc | Not started | 7 | 0 | 7 | 0 | -7
4.09 | PB25 | Test: drug-food warning | Viet, Phuc | Not started | 7 | 0 | 7 | 0 | -7
4.10 | PB26 | Backend: scope lookup API by consent+patient_id | Nguyen | Not started | 5 | 0 | 5 | 0 | -5
4.11 | PB26 | Mobile: Family Member lookup UI | Bao | Not started | 5 | 0 | 5 | 0 | -5
4.12 | PB26 | Test: FM lookup scoping | Viet | Not started | 3 | 0 | 3 | 0 | -3
4.13 | PB27 | Backend: scope drug-drug interaction-check by consent | Nguyen | Not started | 7 | 0 | 7 | 0 | -7
4.14 | PB27 | Mobile: FM interaction warning UI (reuse) | Bao, Nguyen | Not started | 10.5 | 0 | 10.5 | 0 | -10.5
4.15 | PB27 | Test: FM interaction warning | Phuc | Not started | 3.5 | 0 | 3.5 | 0 | -3.5
4.16 | PB28 | Backend: scope drug-food interaction by consent | Viet | Not started | 7 | 0 | 7 | 0 | -7
4.17 | PB28 | Mobile: FM food-warning UI (reuse) | Bao, Viet | Not started | 7 | 0 | 7 | 0 | -7
4.18 | PB28 | Test: FM food-warning | Nguyen | Not started | 3.5 | 0 | 3.5 | 0 | -3.5
4.19 | PB30 | Cross-device test checklist: onboarding/reminder/confirm (Android) | Bao, Viet | Not started | 10 | 0 | 150.5 | 0 | -150.5
4.20 | PB30 | Cross-device test checklist: same flows (iOS) | Nguyen, Duc | Not started | 10 | 0 | 0 | 0 | 0
4.21 | PB30 | Log & triage defects found | Phuc, Bao | Not started | 5 | 0 | 0 | 0 | 0
|  |  |  | Total | 150.5 | 0 | 276 | 0 | -276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 5 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
5.01 | PB31 | Research/evaluate ML Kit text recognition on VN packaging samples | Bao, Duc | Not started | 14 | 0 | 14 | 0 | -14
5.02 | PB31 | Integrate on-device OCR into mobile app | Duc, Viet | Not started | 17.5 | 0 | 17.5 | 0 | -17.5
5.03 | PB31 | Build matching algorithm (OCR text to catalog entry) | Nguyen, Viet | Not started | 21 | 0 | 21 | 0 | -21
5.04 | PB31 | Build manual-search fallback UI when no match found | Bao, Duc | Not started | 14 | 0 | 14 | 0 | -14
5.05 | PB31 | Log unmatched items for Admin catalog review | Nguyen | Not started | 7 | 0 | 7 | 0 | -7
5.06 | PB31 | Test: OCR accuracy across multiple packaging samples | Phuc | Not started | 5 | 0 | 5 | 0 | -5
5.07 | PB32 | Mobile: confirmation step showing matched catalog entry | Bao, Duc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.08 | PB32 | Test: confirmation step cannot be skipped | Phuc, Viet | Not started | 6.5 | 0 | 6.5 | 0 | -6.5
5.09 | PB33 | Mobile: Simple Mode toggle (persists across sessions) | Bao | Not started | 6 | 0 | 6 | 0 | -6
5.10 | PB33 | Mobile: simplified screen (next dose + single confirm button) | Bao, Duc | Not started | 15 | 0 | 15 | 0 | -15
5.11 | PB33 | Mobile: high-contrast theme + font scaling | Duc | Not started | 6 | 0 | 6 | 0 | -6
5.12 | PB33 | Test: Simple Mode UX flow | Phuc | Not started | 5 | 0 | 5 | 0 | -5
5.13 | PB34 | Backend: deletion-request record creation API | Nguyen, Viet | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.14 | PB34 | Mobile: settings action for withdraw consent / delete data | Phuc, Bao | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.15 | PB34 | Test: confirmation shown immediately to patient | Phuc, Viet | Not started | 6.5 | 0 | 6.5 | 0 | -6.5
5.16 | PB35 | Backend: Admin queue API for pending requests | Nguyen, Phuc | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.17 | PB35 | Admin dashboard: request queue UI | Phuc, Nguyen | Not started | 10 | 0 | 10 | 0 | -10
5.18 | PB35 | Backend: trigger actual data-deletion job on 'processed' | Viet | Not started | 5 | 0 | 5 | 0 | -5
5.19 | PB36 | Backend: log entry on every FM/Admin sensitive-data view | Nguyen, Viet | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.20 | PB36 | Admin dashboard: access log viewer UI (filterable) | Phuc, Bao | Not started | 7.5 | 0 | 7.5 | 0 | -7.5
5.21 | PB36 | Test: log entries created correctly | Viet | Not started | 3 | 0 | 3 | 0 | -3
|  |  |  | Total | 186.5 | 0 | 186.5 | 0 | -186.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5 | 186.5
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 5 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 6 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
6.01 | PB37 | Backend: LLM API integration (meal-suggestion prompt + parsing) | Nguyen, Viet | Not started | 17.5 | 0 | 17.5 | 0 | -17.5
6.02 | PB37 | Backend: mandatory disclaimer injection logic | Phuc | Not started | 7 | 0 | 7 | 0 | -7
6.03 | PB37 | Mobile: meal suggestion UI | Bao, Duc | Not started | 14 | 0 | 14 | 0 | -14
6.04 | PB37 | Test: disclaimer always shown, latency acceptable | Viet | Not started | 5 | 0 | 5 | 0 | -5
6.05 | PB39 | Backend: scope meal-suggestion by consent+patient_id | Nguyen, Bao | Not started | 4 | 0 | 4 | 0 | -4
6.06 | PB39 | Mobile: Family Member meal suggestion UI (reuse) | Duc | Not started | 4 | 0 | 4 | 0 | -4
6.07 | PB39 | Test: FM meal suggestion scoping | Bao | Not started | 3 | 0 | 3 | 0 | -3
6.08 | PB41 | Update DPIA with final implemented data flows (AI API + OCR + cross-border assessment), based on S1 preliminary draft | Phuc, Nguyen | Not started | 14 | 0 | 14 | 0 | -14
6.09 | PB41 | Review DPIA with mentor | Phuc | Not started | 7 | 0 | 7 | 0 | -7
6.10 | PB41 | Finalize and sign off DPIA | Phuc, Nguyen | Not started | 7 | 0 | 7 | 0 | -7
6.11 | PB42 | Compliance checklist review (all sensitive-data flows) | Nguyen, Phuc | Not started | 14 | 0 | 14 | 0 | -14
6.12 | PB42 | Log and resolve any compliance gap found | Nguyen, Viet | Not started | 10.5 | 0 | 10.5 | 0 | -10.5
6.13 | PB43 | Retest all Sprint 1-5 features end-to-end | Bao, Duc | Not started | 21 | 0 | 21 | 0 | -21
6.14 | PB43 | Fix Critical/High severity bugs | Bao, Duc, Viet | Not started | 28 | 0 | 28 | 0 | -28
6.15 | PB43 | Fix Medium/Low severity bugs (time permitting) | Duc, Bao | Not started | 14 | 0 | 14 | 0 | -14
6.16 | PB43 | Final regression test before Integration phase | Viet, Phuc | Not started | 7 | 0 | 7 | 0 | -7
|  |  |  | Total | 177 | 0 | 177 | 0 | -177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Team member 1 | [16 empty] | 0
[8 empty] | Team member 2 | [16 empty] | 0
[8 empty] | Team member 3 | [16 empty] | 0
[8 empty] | Team member 4 | [16 empty] | 0
[8 empty] | Team member 5 | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 6 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms