## Main
Scrum Project
Product | DrugTime
Active versions | v1.0
Team |  |  | Product Owner | Nguyen Van Nguyen
Scrum Master | Nguyen Ngoc Phuc |  | Other Stakeholders | B.Eng. Nguyen Trong Giap
Developers | Nguyen Ngoc Phuc
Nguyen Van Nguyen
Nguyen Quang Bao
Nguyen Tan Duc
Dang Ngo Ngoc Viet
Projects | [5 empty] | Sprint Plan
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
1 | DrugTime MVP (Capstone Project 1) | 2026-09-10 | 2026-12-06 | In Progress | Implementation only | 1 | 2026-09-14 | 2026-09-27 | Not started | 107
2 | DrugTime - Full Project (Initiation to Capstone Defense) | 2026-09-10 | 2026-12-26 | In Progress |  | 2 | 2026-09-28 | 2026-10-11 | Not started | 4
[6 empty] | 3 | 2026-10-12 | 2026-10-25 | Not started | 122
[6 empty] | 4 | 2026-10-26 | 2026-11-08 | Not started | 117
[6 empty] | 5 | 2026-11-09 | 2026-11-22 | Not started | 125
[6 empty] | 6 | 2026-11-23 | 2026-12-06 | Not started | 125
Formulas:
End = [Start]+13
Start = [End, row above]+1

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register / Login | Patient | Register and log into my account | I can securely access the app | - POST /auth/register + /auth/login return 200/401 correctly - Password hashed, session token issued - Mobile UI: form validation, error states | Hỗ trợ đăng nhập bằng cả email và SĐT (users.email thêm ở Schema v4). | 1 | Not started | User Story | 1 | 1 | 17
PB02 | Purpose-separated consent | Patient | Complete consent separately for each data-processing purpose | My data is only used for what I explicitly agreed to (PDPL 2025) | - DB table `consents` stores purpose, granted_at - UI: one toggle per purpose, no 'Accept All' button - Backend blocks data action if purpose not consented - Revoking one purpose does not affect consent already granted for other purposes |  | 1 | Not started | User Story | 1 | 1 | 16
PB03 | Manage health profile | Patient | Create and edit my health profile | The system has accurate info to base reminders and warnings on | - CRUD /profile endpoint - Mobile form with validation |  | 1 | Not started | User Story | 1 | 3 | 12
PB04 | Manage medication catalog | Admin | Add, edit, and remove medications in the catalog | Patients can match their medications against an accurate list | - Admin dashboard CRUD table - Search/filter by name - Soft-delete only: entries referenced by existing patient history cannot be hard-deleted (avoid breaking historical records) |  | 1 | Not started | User Story | 1 | 2 | 14
PB05 | Manage interaction catalog | Admin | Add, edit, and remove drug-drug/drug-food interaction records | Interaction warnings shown to patients are accurate | - Admin dashboard CRUD table - Linked to medication catalog by ID - Soft-delete only: entries referenced by existing patient history cannot be hard-deleted (avoid breaking historical records) |  | 1 | Not started | User Story | 1 | 2 | 14
PB06 | Synchronize catalog from external sources | Admin | Trigger a periodic sync job pulling from the Vietnamese Drug Regulatory Data Source | The catalog stays current without manual re-entry | - RQ scheduled job runs weekly/monthly - Sync log stored with timestamp + record count | Task split: research+build in S1, logging+testing in S2 | 1 | Not started | User Story | 1 | 1 | 34
PB07 | Backend deployment on Render | Team | Have the backend deployed to Render | The mobile app and admin dashboard reach a public HTTPS backend, and every push to main redeploys without manual steps | - Render Web Service builds from the GitHub repo and auto-deploys on push to main - Health-check endpoint returns 200; HTTPS provided by Render - Secrets set as Render environment variables (none in the repo) - RQ jobs (catalog sync, missed-dose detection) run on Render - Mobile app + admin dashboard smoke-tested against the Render URL | Task split: deploy + smoke test in S4; final redeploy + runbook in S6. Replaces GitHub Actions / Oracle Cloud VM / Caddy (dropped). | 1 | Not started | Technical Task | 1 | 4 | 18
PB08 | Database schema design & migrations | Team | Have a versioned DB schema | All modules share a consistent, evolvable data model | - ERD reviewed & approved - Migration scripts run cleanly on empty DB |  | 1 | Not started | Technical Task | 1 | 1 | 23
PB09 | Patient-Family linking data model | Team | Have a many-to-many linking table between patients and family members | Sprint 3 features (linking, alerts) have a schema to build on | - Table `patient_family_links` with status/consent fields - Unit tested for many-to-many |  | 1 | Not started | Technical Task | 1 | 2 | 12
PB10 | Add medication (manual input) | Patient | Add a medication by entering its name, dose, and schedule manually | I can start tracking a medication without scanning | - POST /medications validates required fields - Mobile form: name, dose, time, frequency | Chỉ chọn thuốc có sẵn trong danh mục (medication_id bắt buộc, Schema v5) — không còn cho nhập tự do. | 1 | Not started | User Story | 1 | 2 | 18
PB11 | Manage medication schedule | Patient | Edit the time, dose, and frequency of a medication | My schedule stays accurate as prescriptions change | - PUT /medications/{id}/schedule - UI supports edit/delete of a schedule entry |  | 1 | Not started | User Story | 1 | 2 | 15
PB12 | Receive reminder | Patient | Get a local notification at each scheduled dose time | I don't forget to take my medication | - Local notification fires within 2s of scheduled time (NFR05) - Works offline (on-device scheduling) - No reminder sent if the dose was already confirmed before the scheduled time - Correct handling when multiple medications share the same reminder time (all shown, none dropped) |  | 1 | Not started | User Story | 1 | 2 | 24
PB13 | Confirm dose intake | Patient | Tap a button to confirm I took a dose | My adherence is tracked accurately | - Button confirmation writes to adherence log - Confirmed state reflected in reminder UI immediately |  | 1 | Not started | User Story | 1 | 2 | 12
PB14 | View adherence history | Patient | See a log of doses taken/missed by day and by medication | I can track my own consistency | - GET /adherence returns list grouped by date+medication - Mobile screen renders calendar/list view |  | 1 | Not started | User Story | 1 | 3 | 12
PB15 | Link family member | Patient | Generate a QR code or referral code to link a family member | They can monitor my adherence | - GET /family/link-code returns the user's fixed link code + QR payload - One fixed, non-expiring code per user (QD-04) |  | 2 | Not started | User Story | 1 | 3 | 14
PB16 | Confirm data-sharing consent on linking | Patient | Confirm what data is shared when a family member links | Sharing stays within the purpose I explicitly agreed to | - Linking flow blocked until consent confirmed - Consent record linked to the specific family member ID |  | 1 | Not started | User Story | 1 | 3 | 10
PB17 | Remove linked family member | Patient | Remove a previously linked family member | I can revoke their access at any time | - DELETE /links/{id} removes access immediately - Family member's app reflects the change on next sync |  | 2 | Not started | User Story | 1 | 3 | 6
PB18 | Revoke data-sharing permission | Patient | Revoke data-sharing without fully removing the link | I can pause sharing without ending the relationship | - PATCH /links/{id}/consent sets shared=false - Family member's Drug Safety Lookup access blocked immediately |  | 2 | Not started | User Story | 1 | 3 | 6
PB19 | Link to patient account | Family Member | Scan a QR code or enter a referral code to link to a patient | I can start monitoring them | - POST /family/link-requests validates code, creates a pending link request; patient must approve (QD-04) - No cap on number of linked patients |  | 2 | Not started | User Story | 1 | 3 | 12
PB20 | Receive missed-dose alert | Family Member | Get a real-time alert when a linked patient misses a dose | I can check on them promptly | - Push notification within 2s of missed-dose detection - Alert names the patient explicitly - No missed-dose alert sent if the patient confirms the dose just before the detection job runs (avoid false alert to Family Member) |  | 1 | Not started | User Story | 1 | 3 | 26
PB21 | View adherence history | Family Member | View basic adherence history of a linked patient | I can understand their consistency over time | - GET /adherence?patient_id= scoped by active consent - Blocked if consent revoked |  | 1 | Not started | User Story | 1 | 3 | 10
PB22 | Manage multiple linked patients | Family Member | Switch between multiple linked patients in the app | I can monitor more than one family member | - Patient-switcher UI component - Data scoped correctly per selected patient (no data leak) |  | 2 | Not started | User Story | 1 | 5 | 24
PB23 | Look up medication information | Patient | Search for and view details of a medication | I understand what I'm taking | - GET /medications/search?q= - Result includes dosage form, active ingredient |  | 1 | Not started | User Story | 1 | 3 | 12
PB24 | View drug-drug interaction warning | Patient | See a warning if two of my medications interact | I'm alerted to a potential safety risk | - Warning screen triggered on medication add if conflict found - Mandatory disclaimer text always shown (NFR03) - Interaction-detection logic validated against a standardized drug-drug interaction test-case set (must cover true-positive pairs, true-negative/no-interaction pairs, and known edge cases), not just UI text presence - Test case set reviewed/approved by mentor before Sprint 4 acceptance - Multiple simultaneous interactions: all conflicting pairs are listed, not only the first match found - UI distinguishes 3 result states, each with a distinct, clearly worded message: (1) Interaction found -> warning shown; (2) Not found within checked data -> neutral wording (e.g. 'no known interaction in current database'), never phrased as a guarantee of safety; (3) Insufficient data (e.g. medication/food not in catalog) -> explicit 'cannot verify, please consult a pharmacist' message, not silently treated as 'no interaction' |  | 1 | Not started | User Story | 1 | 4 | 21
PB25 | View drug-food interaction warning | Patient | See a warning if a medication interacts with a food | I can avoid risky food combinations | - Warning shown in AI meal suggestion + standalone lookup - Mandatory disclaimer text always shown - Detection logic validated against the same standardized test-case approach as PB24 (true-positive/true-negative food-drug pairs) - Multiple conflicting foods in one meal suggestion are all surfaced, not only the first match found - UI distinguishes 3 result states, each with a distinct, clearly worded message: (1) Interaction found -> warning shown; (2) Not found within checked data -> neutral wording (e.g. 'no known interaction in current database'), never phrased as a guarantee of safety; (3) Insufficient data (e.g. medication/food not in catalog) -> explicit 'cannot verify, please consult a pharmacist' message, not silently treated as 'no interaction' |  | 1 | Not started | User Story | 1 | 4 | 17
PB26 | Look up medication info of linked patient | Family Member | Search medication info for a linked patient | I can help them understand their treatment | - Same as Patient lookup, scoped by consent+patient_id - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 5 | 8
PB27 | View drug-drug interaction of linked patient | Family Member | View drug-drug warnings for a linked patient | I can help spot safety risks | - Reuses Patient interaction logic, scoped by consent - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 5 | 14
PB28 | View drug-food interaction of linked patient | Family Member | View drug-food warnings for a linked patient | I can help with meal planning for them | - Reuses Patient interaction logic, scoped by consent - Access is re-checked against current consent status on every API call, not cached for the session |  | 2 | Not started | User Story | 1 | 5 | 12
PB29 | iOS build/signing pipeline setup | Team | Have a working iOS build and TestFlight/Ad Hoc signing pipeline | The MVP can ship on both Android and iOS as committed | - Mac build produces signed .ipa - Installable via TestFlight or Ad Hoc | Team chốt KHÔNG mua Apple Developer Program cho Phase 1: chỉ dùng Apple ID miễn phí. AC 'installable via TestFlight or Ad Hoc' không đạt được; chỉ chạy qua Xcode trên máy thật. Hệ quả: PB20 không có push (APNs) trên iOS. | 1 | Not started | Technical Task | 1 | 1 | 27
PB30 | Cross-device testing (Android + iOS) | Team | Run core flows on real Android and iOS devices | We catch platform-specific bugs before later sprints | - Test checklist covers onboarding, reminder, confirmation on both OS - Defects logged in tracker |  | 1 | Not started | Technical Task | 1 | 4 | 17
PB31 | Scan blister pack | Patient | Scan a medication blister pack with the camera | I can add a medication faster than typing it | - On-device ML Kit recognition, no image leaves device - Falls back to manual search if no match (Risk R-01) - Recognition-confidence threshold defined; below it, auto-fallback to manual search instead of showing a possibly-wrong match | Không khớp danh mục -> chuyển tìm thủ công (không nhập tự do). Bảng log unmatched_scan_logs đã bị bỏ khỏi Schema v6 để đơn giản hoá (mất khả năng Admin tự động biết thuốc nào cần bổ sung). | 1 | Not started | User Story | 1 | 4 | 52
PB32 | Confirm medication | Patient | Manually verify a scanned or entered medication before saving | Incorrect matches don't silently enter my schedule | - Confirmation step is mandatory, cannot be skipped - Shows matched catalog entry for review |  | 1 | Not started | User Story | 1 | 5 | 9
PB33 | Switch to Simple Mode UI | Patient | Switch to a high-contrast, single-button interface | I can use the app easily despite low tech literacy | - Toggle in settings persists across sessions - Simple Mode screen shows only next dose + 1 confirm button | Trạng thái Simple Mode lưu cục bộ trên máy (SharedPreferences/UserDefaults), KHÔNG lưu server — Schema v3 đã bỏ cột users.che_do_nguoi_cao_tuoi. | 2 | Not started | User Story | 1 | 6 | 21
PB34 | Withdraw consent / request data deletion | Patient | Withdraw consent or request my data be deleted | I retain control over my personal data (PDPL 2025) | - Settings action triggers deletion request record - Confirmation shown to patient immediately |  | 1 | Not started | User Story | 1 | 5 | 14
PB35 | Process data deletion / consent withdrawal requests | Admin | View and process pending deletion/withdrawal requests | Compliance obligations are met within a defined SLA | - Admin queue lists pending requests - Marking 'processed' triggers actual data deletion job |  | 1 | Not started | User Story | 1 | 5 | 15
PB36 | View sensitive-data access log | Admin | View a log of who accessed a patient's sensitive health data | The system is auditable under DPIA obligations | - Log entry created on every Family Member/Admin data view - Filterable by patient, date, actor |  | 2 | Not started | User Story | 1 | 6 | 12
PB37 | View AI meal suggestion with explanation | Patient | See a suggested meal based on my current medications, with a brief explanation | I can make safer dietary choices | - LLM API call returns suggestion + explanation within 10 seconds latency - Medical disclaimer always shown (R-07) - Meal suggestion distinguishes the same 3 states for food-drug conflict checks (found / not found in checked data / insufficient data), never silently defaulting to 'safe' |  | 1 | Not started | User Story | 1 | 5 | 29
PB39 | View AI meal suggestion for linked patient | Family Member | View the AI meal suggestion generated for a linked patient | I can help plan meals for them | - Reuses Patient meal-suggestion endpoint, scoped by consent |  | 2 | Not started | User Story | 1 | 6 | 8
PB41 | Conduct DPIA for new sensitive-data flows | Admin | Complete a Data Protection Impact Assessment before go-live | The platform is compliant with the 2025 PDPL before launch | - DPIA document completed and reviewed with mentor - Signed off before Sprint 6 ends | Task split: preliminary draft in S1, update+review+signoff in S6 | 1 | Not started | User Story | 1 | 6 | 25
PB42 | Review PDPL 2025 / Decree 356 compliance | Admin | Review the full platform against PDPL 2025 and Decree 356 requirements | No compliance gap remains before final submission | - Compliance checklist completed - Any gap logged and resolved before Final Submission |  | 1 | Not started | User Story | 1 | 6 | 16
PB43 | Full-system bug-fixing (Android + iOS) | Team | Fix defects found during end-to-end testing | The final submission is stable on both platforms | - All Sprint 1-6 features retested end-to-end - Critical/High bugs resolved before Integration phase |  | 1 | Not started | Technical Task | 1 | 6 | 46
[11 empty] | Total | 724
Note on M7: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.01 | PB08 | Design ERD | Phuc, Nguyen | Done | 11 | 0 | 11 | 0 | -11 | Day 1: 9; Day 2: 3; Day 3: 0
1.02 | PB08 | Write Supabase migration scripts | Nguyen | Done | 7 | 0 | 7 | 0 | -7 | Day 3: 5; Day 4: 0
1.03 | PB08 | Review & test migrations on clean DB | Nguyen | Done | 7 | 0 | 7 | 0 | -7 | Day 5: 0
1.07 | PB29 | Confirm Mac access + configure free Apple ID in Xcode | Nguyen | Done | 5 | 0 | 5 | 0 | -5
1.08 | PB29 | Configure Xcode project + automatic signing |  | Done | 11 | 0 | 11 | 0 | -11
1.09 | PB29 | Test: build & run app on real device via Xcode (USB/Wi-Fi debugging) | Phuc | Done | 7 | 0 | 7 | 0 | -7
1.10 | PB01 | Backend: Supabase Auth integration (register/login API) |  | Done | 5 | 0 | 5 | 0 | -5
1.11 | PB01 | Mobile: Register/Login UI screens |  | Done | 7 | 0 | 7 | 0 | -7
1.12 | PB01 | Mobile-Backend integration + error handling |  | Done | 3 | 0 | 3 | 0 | -3
1.13 | PB01 | Test: unit + widget test |  | Done | 2 | 0 | 2 | 0 | -2
1.14 | PB02 | Backend: consents table + grant/revoke API per purpose |  | Not started | 7 | 0 | 7 | 0 | -7
1.15 | PB02 | Mobile: consent UI (per-purpose toggles, no 'Accept All') |  | Not started | 6 | 0 | 6 | 0 | -6
1.16 | PB02 | Test: consent flow end-to-end |  | Not started | 3 | 0 | 3 | 0 | -3
1.17 | PB06 | Research/parse Vietnamese Drug Regulatory Data Source structure |  | Done | 20 | 0 | 20 | 0 | -20
1.18 | PB41 | Draft preliminary DPIA (based on planned sensitive-data flows) | Phuc | Done | 6 | 0 | 6 | 0 | -6
|  |  |  | Total | 107 | 0 | 107 | 0 | -107 | 9 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 98 | 95 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
|  |  |  | Burn up | [5 empty] | 9 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2.01 | PB10 | Backend: Add, edi medication API + validation | Nguyên | Not started | 14 | 0 | 14 | 0 | -14
2.02 | PB10 | Mobile: Add medication form UI | Nguyên | Not started | 10 | 0 | 10 | 0 | -10
2.03 | PB10 | Test: unit + widget test (add medication) | Việt | Not started | 8 | 0 | 8 | 0 | -8
2.04 | PB11 | Backend: medication schedule CRUD API | Nguyên | Not started | 10 | 0 | 10 | 0 | -10
2.05 | PB11 | Mobile: medication detail & edit UI | Phúc | Done | 10 | 0 | 10 | 0 | -10 | Day 1: 9; Day 2: 4; Day 3: 0
2.06 | PB11 | Test: schedule CRUD | Nguyên | Not started | 10 | 0 | 10 | 0 | -10
2.07 | PB12 | Mobile: Reminder Scheduler — lên lịch local notification (flutter_local_notifications), dùng dữ liệu lịch từ Local Store (2.23) | Đức | Not started | 14 | 0 | 14 | 0 | -14
2.08 | PB12 | Mobile: notification edge cases (timezone, multi-dose/day) | Đức | Not started | 10 | 0 | 10 | 0 | -10
2.09 | PB12 | Test: verify reminder fires within 2s (NFR05) | Đức | Not started | 12 | 0 | 12 | 0 | -12
2.10 | PB13 | Backend: dose confirmation API + adherence log write | Bảo | Not started | 10 | 0 | 10 | 0 | -10
2.11 | PB13 | Mobile: Dose Confirmation UI — nút xác nhận + cập nhật trạng thái, đẩy vào Outbox (2.24) | Phúc | Not started | 6 | 0 | 6 | 0 | -6
2.12 | PB13 | Test: confirm dose flow end-to-end | Đức | Not started | 4 | 0 | 4 | 0 | -4
2.13 | PB04 | Backend: medication catalog CRUD API | Việt | Not started | 10 | 0 | 10 | 0 | -10
2.14 | PB04 | Admin dashboard: catalog table UI (React/Next.js) | Việt | Not started | 10 | 0 | 10 | 0 | -10
2.15 | PB04 | Test: catalog CRUD | Phúc | Not started | 4 | 0 | 4 | 0 | -4
2.16 | PB05 | Backend: interaction catalog CRUD API | Nguyên | Not started | 12 | 0 | 12 | 0 | -12
2.17 | PB05 | Admin dashboard: interaction catalog UI | Việt | Not started | 12 | 0 | 12 | 0 | -12
2.18 | PB05 | Test: interaction catalog CRUD | Việt | Not started | 4 | 0 | 4 | 0 | -4
2.19 | PB09 | Backend: unit test many-to-many linking logic | Bảo | Not started | 12 | 0 | 12 | 0 | -12
2.20 | PB06 | Sync logging + error handling | Bảo | Not started | 12 | 0 | 12 | 0 | -12
2.21 | PB06 | Build RabbitMQ scheduled sync job | Phúc | Not started | 24 | 0 | 24 | 0 | -24
2.22 | PB06 | Test sync job end-to-end | Phúc | Not started | 8 | 0 | 8 | 0 | -8
2.23 | PB12 | Mobile: Local Store — lưu lịch uống thuốc & liều cục bộ (mã hoá) | Bảo | Not started | 8 | 0 | 8 | 0 | -8
2.24 | PB13 | Mobile: Outbox — hàng đợi xác nhận liều chờ đồng bộ (client_uuid) | Đức | Not started | 4 | 0 | 4 | 0 | -4
2.25 | PB13 | Mobile: Sync Engine — đồng bộ Outbox khi có mạng (retry/backoff, ≤30s) | Bảo | Not started | 2 | 0 | 2 | 0 | -2
|  |  |  | Total | 240 | 0 | 240 | 0 | -240 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 231 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227 | 227
|  |  |  | Burn up | [5 empty] | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 120
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
| Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
3.01 | PB14 | Backend: GET /adherence (group by date/medication) |  | Not started | 5 | 0 | 5 | 0 | -5
3.02 | PB14 | Mobile: adherence calendar/list UI |  | Not started | 5 | 0 | 5 | 0 | -5
3.03 | PB14 | Test: adherence history |  | Not started | 2 | 0 | 2 | 0 | -2
3.04 | PB23 | Backend: GET /medications/search API |  | Not started | 5 | 0 | 5 | 0 | -5
3.05 | PB23 | Mobile: medication lookup search UI |  | Not started | 5 | 0 | 5 | 0 | -5
3.06 | PB23 | Test: medication lookup |  | Not started | 2 | 0 | 2 | 0 | -2
3.07 | PB03 | Backend: health profile CRUD API |  | Not started | 5 | 0 | 5 | 0 | -5
3.08 | PB03 | Mobile: profile form UI |  | Not started | 5 | 0 | 5 | 0 | -5
3.09 | PB03 | Test: profile CRUD |  | Not started | 2 | 0 | 2 | 0 | -2
3.10 | PB15 | Backend: QR/referral code generation API |  | Not started | 5 | 0 | 5 | 0 | -5
3.11 | PB15 | Mobile: generate & display QR/code UI |  | Not started | 5 | 0 | 5 | 0 | -5
3.12 | PB15 | Test: fixed link code (one per user, non-expiring) |  | Not started | 4 | 0 | 4 | 0 | -4
3.13 | PB19 | Backend: POST /family/link-requests (validate code + create pending link) |  | Not started | 5 | 0 | 5 | 0 | -5
3.14 | PB19 | Mobile: scan QR / enter code UI (Family Member) |  | Not started | 5 | 0 | 5 | 0 | -5
3.15 | PB19 | Test: redeem flow |  | Not started | 2 | 0 | 2 | 0 | -2
3.16 | PB16 | Backend: block linking until consent confirmed |  | Not started | 4 | 0 | 4 | 0 | -4
3.17 | PB16 | Mobile: consent confirmation screen during linking |  | Not started | 4 | 0 | 4 | 0 | -4
3.18 | PB16 | Test: consent-on-link flow |  | Not started | 2 | 0 | 2 | 0 | -2
3.19 | PB20 | Backend: missed-dose detection scheduled job [iOS: không có push do không mua Apple Developer Program] |  | Not started | 9 | 0 | 9 | 0 | -9
3.20 | PB20 | Backend: alert dispatch logic to Family Member [iOS: không có push do không mua Apple Developer Program] |  | Not started | 7 | 0 | 7 | 0 | -7
3.21 | PB20 | Mobile: Family Member alert handling UI [iOS: không có push do không mua Apple Developer Program] |  | Not started | 5 | 0 | 5 | 0 | -5
3.22 | PB20 | Test: alert fires <2s, names patient explicitly [iOS: không có push do không mua Apple Developer Program] |  | Not started | 5 | 0 | 5 | 0 | -5
3.23 | PB21 | Backend: GET /adherence?patient_id= scoped by consent |  | Not started | 5 | 0 | 5 | 0 | -5
3.24 | PB21 | Mobile: Family Member adherence view UI |  | Not started | 3 | 0 | 3 | 0 | -3
3.25 | PB21 | Test: adherence history (Family Member) |  | Not started | 2 | 0 | 2 | 0 | -2
3.26 | PB17 | Backend: DELETE /links/{id} API |  | Not started | 3 | 0 | 3 | 0 | -3
3.27 | PB17 | Mobile: remove-link UI + confirm dialog |  | Not started | 3 | 0 | 3 | 0 | -3
3.28 | PB18 | Backend: PATCH /links/{id}/consent (shared=false) |  | Not started | 3 | 0 | 3 | 0 | -3
3.29 | PB18 | Mobile: toggle data-sharing UI |  | Not started | 3 | 0 | 3 | 0 | -3
2.25 | PB13 | Mobile: Sync Engine — đồng bộ Outbox khi có mạng (retry/backoff, ≤30s) |  | Not started | 2 | 0 | 2
|  |  |  | Total | 122 | 0 | 120 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 4 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
4.01 | PB24 | Backend: drug-drug interaction-check logic |  | Not started | 9 | 0 | 9 | 0 | -9
4.02 | PB24 | Mobile: warning screen UI + mandatory disclaimer |  | Not started | 7 | 0 | 7 | 0 | -7
4.03 | PB24 | Test: validate interaction-detection algorithm against standardized test-case set (true/false positives) + verify disclaimer always shown |  | Not started | 5 | 0 | 5 | 0 | -5
4.04 | PB25 | Backend: drug-food interaction lookup logic |  | Not started | 7 | 0 | 7 | 0 | -7
4.05 | PB25 | Mobile: food-warning screen UI (reuse) |  | Not started | 5 | 0 | 5 | 0 | -5
4.06 | PB25 | Test: drug-food warning |  | Not started | 5 | 0 | 5 | 0 | -5
4.07 | PB31 | Research/evaluate ML Kit text recognition on VN packaging samples |  | Not started | 9 | 0 | 9 | 0 | -9
4.08 | PB31 | Integrate on-device OCR into mobile app |  | Not started | 12 | 0 | 12 | 0 | -12
4.09 | PB31 | Build matching algorithm (OCR text to catalog entry) |  | Not started | 14 | 0 | 14 | 0 | -14
4.10 | PB31 | Build manual-search fallback UI when no match found |  | Not started | 9 | 0 | 9 | 0 | -9
4.11 | PB31 | [ĐÃ GỠ] Log unmatched items for Admin catalog review — bảng unmatched_scan_logs bị bỏ khỏi Schema v6 |  | Removed | 0 | 0 | 0 | 0 | 0
4.12 | PB31 | Test: OCR accuracy across multiple packaging samples |  | Not started | 3 | 0 | 3 | 0 | -3
4.13 | PB07 | Create Render Web Service from GitHub repo + auto-deploy on push |  | Not started | 3 | 0 | 3 | 0 | -3
4.14 | PB07 | Set Render env vars/secrets, prod vs dev config, CORS |  | Not started | 2 | 0 | 2 | 0 | -2
4.15 | PB07 | Run RQ jobs on Render (Key Value + worker/cron): sync, missed-dose |  | Not started | 5 | 0 | 5 | 0 | -5
4.16 | PB07 | Check cold-start impact on <2s alert; choose Render plan |  | Not started | 2 | 0 | 2 | 0 | -2
4.17 | PB07 | Point mobile + admin to Render URL; smoke test Android/iOS |  | Not started | 3 | 0 | 3 | 0 | -3
4.18 | PB30 | Cross-device test checklist: onboarding/reminder/confirm (Android) |  | Not started | 7 | 0 | 7 | 0 | -7
4.19 | PB30 | Cross-device test checklist: same flows (iOS) |  | Not started | 7 | 0 | 7 | 0 | -7
4.20 | PB30 | Log & triage defects found |  | Not started | 3 | 0 | 3 | 0 | -3
|  |  |  | Total | 117 | 0 | 117 | 0 | -117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 5 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
5.01 | PB32 | Mobile: confirmation step showing matched catalog entry |  | Not started | 5 | 0 | 5 | 0 | -5
5.02 | PB32 | Test: confirmation step cannot be skipped |  | Not started | 4 | 0 | 4 | 0 | -4
5.03 | PB34 | Backend: deletion-request record creation API |  | Not started | 5 | 0 | 5 | 0 | -5
5.04 | PB34 | Mobile: settings action for withdraw consent / delete data |  | Not started | 5 | 0 | 5 | 0 | -5
5.05 | PB34 | Test: confirmation shown immediately to patient |  | Not started | 4 | 0 | 4 | 0 | -4
5.06 | PB35 | Backend: Admin queue API for pending requests |  | Not started | 5 | 0 | 5 | 0 | -5
5.07 | PB35 | Admin dashboard: request queue UI |  | Not started | 7 | 0 | 7 | 0 | -7
5.08 | PB35 | Backend: trigger actual data-deletion job on 'processed' |  | Not started | 3 | 0 | 3 | 0 | -3
5.09 | PB37 | Backend: LLM API integration (meal-suggestion prompt + parsing) |  | Not started | 12 | 0 | 12 | 0 | -12
5.10 | PB37 | Backend: mandatory disclaimer injection logic |  | Not started | 5 | 0 | 5 | 0 | -5
5.11 | PB37 | Mobile: meal suggestion UI |  | Not started | 9 | 0 | 9 | 0 | -9
5.12 | PB37 | Test: disclaimer always shown, latency acceptable |  | Not started | 3 | 0 | 3 | 0 | -3
5.13 | PB22 | Backend: list linked patients API |  | Not started | 5 | 0 | 5 | 0 | -5
5.14 | PB22 | Mobile: patient-switcher UI component |  | Not started | 12 | 0 | 12 | 0 | -12
5.15 | PB22 | Mobile: scope data correctly per selected patient |  | Not started | 5 | 0 | 5 | 0 | -5
5.16 | PB22 | Test: verify no cross-patient data leak |  | Not started | 2 | 0 | 2 | 0 | -2
5.17 | PB26 | Backend: scope lookup API by consent+patient_id |  | Not started | 3 | 0 | 3 | 0 | -3
5.18 | PB26 | Mobile: Family Member lookup UI |  | Not started | 3 | 0 | 3 | 0 | -3
5.19 | PB26 | Test: FM lookup scoping |  | Not started | 2 | 0 | 2 | 0 | -2
5.20 | PB27 | Backend: scope drug-drug interaction-check by consent |  | Not started | 5 | 0 | 5 | 0 | -5
5.21 | PB27 | Mobile: FM interaction warning UI (reuse) |  | Not started | 7 | 0 | 7 | 0 | -7
5.22 | PB27 | Test: FM interaction warning |  | Not started | 2 | 0 | 2 | 0 | -2
5.23 | PB28 | Backend: scope drug-food interaction by consent |  | Not started | 5 | 0 | 5 | 0 | -5
5.24 | PB28 | Mobile: FM food-warning UI (reuse) |  | Not started | 5 | 0 | 5 | 0 | -5
5.25 | PB28 | Test: FM food-warning |  | Not started | 2 | 0 | 2 | 0 | -2
|  |  |  | Total | 125 | 0 | 125 | 0 | -125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nguyen Ngoc Phuc | [16 empty] | 0
[8 empty] | Nguyen Van Nguyen | [16 empty] | 0
[8 empty] | Nguyen Quang Bao | [16 empty] | 0
[8 empty] | Dang Ngoc Ngoc Viet | [16 empty] | 0
[8 empty] | Nguyen Tan Duc | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 5 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 6 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
6.01 | PB41 | Update DPIA with final implemented data flows (AI API + OCR + cross-border assessment), based on S1 preliminary draft |  | Not started | 9 | 0 | 9 | 0 | -9
6.02 | PB41 | Review DPIA with mentor |  | Not started | 5 | 0 | 5 | 0 | -5
6.03 | PB41 | Finalize and sign off DPIA |  | Not started | 5 | 0 | 5 | 0 | -5
6.04 | PB33 | Mobile: Simple Mode toggle (persists across sessions) |  | Not started | 4 | 0 | 4 | 0 | -4
6.05 | PB33 | Mobile: simplified screen (next dose + single confirm button) |  | Not started | 10 | 0 | 10 | 0 | -10
6.06 | PB33 | Mobile: high-contrast theme + font scaling |  | Not started | 4 | 0 | 4 | 0 | -4
6.07 | PB33 | Test: Simple Mode UX flow |  | Not started | 3 | 0 | 3 | 0 | -3
6.08 | PB36 | Backend: log entry on every FM/Admin sensitive-data view |  | Not started | 5 | 0 | 5 | 0 | -5
6.09 | PB36 | Admin dashboard: access log viewer UI (filterable) |  | Not started | 5 | 0 | 5 | 0 | -5
6.10 | PB36 | Test: log entries created correctly |  | Not started | 2 | 0 | 2 | 0 | -2
6.11 | PB39 | Backend: scope meal-suggestion by consent+patient_id |  | Not started | 3 | 0 | 3 | 0 | -3
6.12 | PB39 | Mobile: Family Member meal suggestion UI (reuse) |  | Not started | 3 | 0 | 3 | 0 | -3
6.13 | PB39 | Test: FM meal suggestion scoping |  | Not started | 2 | 0 | 2 | 0 | -2
6.14 | PB42 | Compliance checklist review (all sensitive-data flows) |  | Not started | 9 | 0 | 9 | 0 | -9
6.15 | PB42 | Log and resolve any compliance gap found |  | Not started | 7 | 0 | 7 | 0 | -7
6.16 | PB43 | Retest all Sprint 1-6 features end-to-end |  | Not started | 14 | 0 | 14 | 0 | -14
6.17 | PB43 | Fix Critical/High severity bugs |  | Not started | 18 | 0 | 18 | 0 | -18
6.18 | PB43 | Fix Medium/Low severity bugs (time permitting) |  | Not started | 9 | 0 | 9 | 0 | -9
6.19 | PB43 | Final regression test before Integration phase |  | Not started | 5 | 0 | 5 | 0 | -5
6.20 | PB07 | Final Render redeploy: prod env (LLM key) + deployment runbook |  | Not started | 3 | 0 | 3 | 0 | -3
|  |  |  | Total | 125 | 0 | 125 | 0 | -125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
|  |  |  | Burn up | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Team member 1 | [16 empty] | 0
[8 empty] | Team member 2 | [16 empty] | 0
[8 empty] | Team member 3 | [16 empty] | 0
[8 empty] | Team member 4 | [16 empty] | 0
[8 empty] | Team member 5 | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 6 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Replan Log
Replan Log - backend deployment moved to Render, sprint load rebalanced
Every task of the 6 sprints: where it was, where it is now, and why. Hours are the Sprint Backlog estimates.
Load per sprint (hours) | [6 empty] | Assumptions
Sprint | Before | After | Change | Sprint sheet total | Check |  | Estimates re-scaled by ~0.66 and rounded to whole hours so each sprint is ~125h (Sprint 1 lower). Before = original file, After = now.
1 | 196 | 112 | -84 | 107 | 5
2 | 199 | 120 | -79 | 4 | 116 |  | Sprint 1 is already running (14-27 Sep), so it only loses the 3 deployment tasks and gets no new work.
3 | 179.5 | 120 | -59.5 | 122 | -2
4 | 150.5 | 122 | -28.5 | 117 | 5 |  | New Render tasks are proposals - adjust as needed. Sprint 1 task IDs are unchanged; Sprints 2-6 are renumbered (see Old ID).
5 | 186.5 | 125 | -61.5 | 125 | 0
6 | 177 | 125 | -52 | 125 | 0 |  | Priority is Product Backlog column I. P1 comes before P2, except prerequisites (PB15/PB19 are P2 but block P1 PB16/PB20/PB21).
Total | 1088.5 | 724 | -364.5 | 600 | 124
Task changes
New Sprint | New ID | Backlog Id | Priority | New Est (h) | Old Est (h) | Old Sprint | Old ID | Change | Owner | Description | Note
1 | 1.01 | PB08 | 1 | 9 | 14 | 1 | 1.01 | Kept | Phuc, Nguyen | Design ERD (patient, medication, consent, family_link, catalog tables,…)
1 | 1.02 | PB08 | 1 | 7 | 10 | 1 | 1.02 | Kept | Phuc, Nguyen | Write Supabase migration scripts
1 | 1.03 | PB08 | 1 | 7 | 10 | 1 | 1.03 | Kept | Viet, Bao, Duc | Review & test migrations on clean DB
1 | 1.07 | PB29 | 1 | 5 | 7 | 1 | 1.07 | Kept | Duc, Phuc | Confirm Mac access + configure free Apple ID in Xcode
1 | 1.08 | PB29 | 1 | 11 | 17 | 1 | 1.08 | Kept | Duc, Phuc | Configure Xcode project + automatic signing
1 | 1.09 | PB29 | 1 | 11 | 17 | 1 | 1.09 | Kept | Duc, Phuc | Test: build & run app on real device via Xcode (USB/Wi-Fi debugging)
1 | 1.10 | PB01 | 1 | 5 | 7 | 1 | 1.10 | Kept | Nguyen, Bao | Backend: Supabase Auth integration (register/login API)
1 | 1.11 | PB01 | 1 | 7 | 10 | 1 | 1.11 | Kept | Bao, Duc | Mobile: Register/Login UI screens
1 | 1.12 | PB01 | 1 | 3 | 5 | 1 | 1.12 | Kept | Bao, Duc | Mobile-Backend integration + error handling
1 | 1.13 | PB01 | 1 | 2 | 3 | 1 | 1.13 | Kept | Bao, Duc | Test: unit + widget test
1 | 1.14 | PB02 | 1 | 7 | 10 | 1 | 1.14 | Kept | Viet, Phuc | Backend: consents table + grant/revoke API per purpose
1 | 1.15 | PB02 | 1 | 6 | 9 | 1 | 1.15 | Kept | Viet, Phuc | Mobile: consent UI (per-purpose toggles, no 'Accept All')
1 | 1.16 | PB02 | 1 | 3 | 5 | 1 | 1.16 | Kept | Viet, Phuc | Test: consent flow end-to-end
1 | 1.17 | PB06 | 1 | 9 | 14 | 1 | 1.17 | Kept | All team member | Research/parse Vietnamese Drug Regulatory Data Source structure
1 | 1.18 | PB06 | 1 | 14 | 21 | 1 | 1.18 | Kept | All team member | Build RQ scheduled sync job
1 | 1.19 | PB41 | 1 | 6 | 10 | 1 | 1.19 | Kept | Phuc, Nguyen | Draft preliminary DPIA (based on planned sensitive-data flows)
2 | 2.01 | PB10 | 1 | 7 | 10 | 2 | 2.01 | Kept | Nguyen, Viet | Backend: Add medication API + validation
2 | 2.02 | PB10 | 1 | 7 | 10 | 2 | 2.02 | Kept | Bao, Duc | Mobile: Add medication form UI
2 | 2.03 | PB10 | 1 | 4 | 6 | 2 | 2.03 | Kept | Bao, Duc | Test: unit + widget test (add medication)
2 | 2.04 | PB11 | 1 | 5 | 7 | 2 | 2.04 | Kept | Nguyen, Phuc | Backend: medication schedule CRUD API
2 | 2.05 | PB11 | 1 | 5 | 7 | 2 | 2.05 | Kept | Bao, Duc | Mobile: schedule edit UI
2 | 2.06 | PB11 | 1 | 5 | 7 | 2 | 2.06 | Kept | Duc, Viet | Test: schedule CRUD
2 | 2.07 | PB12 | 1 | 11 | 17 | 2 | 2.07 | Kept | Bao, Duc | Mobile: local notification scheduling (flutter_local_notifications)
2 | 2.08 | PB12 | 1 | 7 | 10 | 2 | 2.08 | Kept | Bao, Phuc | Mobile: notification edge cases (timezone, multi-dose/day)
2 | 2.09 | PB12 | 1 | 6 | 9 | 2 | 2.09 | Kept | Viet, Phuc | Test: verify reminder fires within 2s (NFR05)
2 | 2.10 | PB13 | 1 | 5 | 8 | 2 | 2.10 | Kept | Nguyen, Viet | Backend: dose confirmation API + adherence log write
2 | 2.11 | PB13 | 1 | 5 | 8 | 2 | 2.11 | Kept | Bao, Duc | Mobile: confirm button UI + state update
2 | 2.12 | PB13 | 1 | 2 | 3 | 2 | 2.12 | Kept | Duc, Nguyen | Test: confirm dose flow end-to-end
2 | 2.13 | PB04 | 1 | 5 | 8 | 2 | 2.16 | Kept | Phuc, Nguyen, Viet | Backend: medication catalog CRUD API
2 | 2.14 | PB04 | 1 | 7 | 10 | 2 | 2.17 | Kept | Nguyen, Bao | Admin dashboard: catalog table UI (React/Next.js)
2 | 2.15 | PB04 | 1 | 2 | 3 | 2 | 2.18 | Kept | Phuc, Duc | Test: catalog CRUD
2 | 2.16 | PB05 | 1 | 5 | 8 | 2 | 2.19 | Kept | Phuc, Duc | Backend: interaction catalog CRUD API
2 | 2.17 | PB05 | 1 | 7 | 10 | 2 | 2.20 | Kept | Phuc, Duc | Admin dashboard: interaction catalog UI
2 | 2.18 | PB05 | 1 | 2 | 3 | 2 | 2.21 | Kept | Phuc, Duc | Test: interaction catalog CRUD
2 | 2.19 | PB09 | 1 | 6 | 10 | 2 | 2.22 | Kept | Phuc, Nguyen, Viet | Backend: design & build patient_family_links table
2 | 2.20 | PB09 | 1 | 6 | 10 | 2 | 2.23 | Kept | Phuc, Nguyen, Viet | Backend: unit test many-to-many linking logic
2 | 2.21 | PB06 | 1 | 6 | 10 | 2 | 2.24 | Kept | Duc, Viet | Sync logging + error handling
2 | 2.22 | PB06 | 1 | 5 | 7 | 2 | 2.25 | Kept | Duc | Test sync job end-to-end
3 | 3.01 | PB14 | 1 | 5 | 7.5 | 3 | 3.01 | Kept | Phuc, Viet | Backend: GET /adherence (group by date/medication)
3 | 3.02 | PB14 | 1 | 5 | 7.5 | 3 | 3.02 | Kept | Bao, Duc | Mobile: adherence calendar/list UI
3 | 3.03 | PB14 | 1 | 2 | 3 | 3 | 3.03 | Kept | Nguyen, Viet | Test: adherence history
3 | 3.04 | PB23 | 1 | 5 | 7.5 | 4 | 4.01 | Moved | Nguyen, Viet | Backend: GET /medications/search API | P1 pulled earlier; catalog and sync are ready after S2
3 | 3.05 | PB23 | 1 | 5 | 7.5 | 4 | 4.02 | Moved | Bao, Duc | Mobile: medication lookup search UI | P1 pulled earlier; catalog and sync are ready after S2
3 | 3.06 | PB23 | 1 | 2 | 3 | 4 | 4.03 | Moved | Phuc | Test: medication lookup | P1 pulled earlier; catalog and sync are ready after S2
3 | 3.07 | PB03 | 1 | 5 | 8 | 2 | 2.13 | Moved | Nguyen | Backend: health profile CRUD API | Deferred from S2 to balance S2 load; not needed by other S2 work
3 | 3.08 | PB03 | 1 | 5 | 7 | 2 | 2.14 | Moved | Nguyen, Bao | Mobile: profile form UI | Deferred from S2 to balance S2 load; not needed by other S2 work
3 | 3.09 | PB03 | 1 | 2 | 3 | 2 | 2.15 | Moved | Nguyen | Test: profile CRUD | Deferred from S2 to balance S2 load; not needed by other S2 work
3 | 3.10 | PB15 | 2 | 5 | 7.5 | 3 | 3.04 | Kept | Nguyen, Phuc | Backend: QR/referral code generation API | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.11 | PB15 | 2 | 5 | 7.5 | 3 | 3.05 | Kept | Bao, Duc | Mobile: generate & display QR/code UI | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.12 | PB15 | 2 | 4 | 6.5 | 3 | 3.06 | Kept | Viet, Phuc | Test: fixed link code (one per user, non-expiring) | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.13 | PB19 | 2 | 5 | 7.5 | 3 | 3.14 | Kept | Nguyen, Phuc | Backend: POST /family/link-requests (validate code + create pending link) | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.14 | PB19 | 2 | 5 | 7.5 | 3 | 3.15 | Kept | Bao, Duc | Mobile: scan QR / enter code UI (Family Member) | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.15 | PB19 | 2 | 2 | 3 | 3 | 3.16 | Kept | Viet | Test: redeem flow | P2, but prerequisite of PB16/PB20/PB21 (P1), so it stays first in S3
3 | 3.16 | PB16 | 1 | 4 | 5 | 3 | 3.07 | Kept | Nguyen, Viet | Backend: block linking until consent confirmed
3 | 3.17 | PB16 | 1 | 4 | 5 | 3 | 3.08 | Kept | Bao, Nguyen | Mobile: consent confirmation screen during linking
3 | 3.18 | PB16 | 1 | 2 | 3 | 3 | 3.09 | Kept | Phuc, Viet | Test: consent-on-link flow
3 | 3.19 | PB20 | 1 | 9 | 14 | 3 | 3.17 | Kept | Phuc, Viet | Backend: missed-dose detection scheduled job
3 | 3.20 | PB20 | 1 | 7 | 10.5 | 3 | 3.18 | Kept | Nguyen, Viet | Backend: alert dispatch logic to Family Member
3 | 3.21 | PB20 | 1 | 5 | 7 | 3 | 3.19 | Kept | Bao, Duc | Mobile: Family Member alert handling UI
3 | 3.22 | PB20 | 1 | 5 | 7 | 3 | 3.20 | Kept | Phuc, Viet | Test: alert fires <2s, names patient explicitly
3 | 3.23 | PB21 | 1 | 5 | 7.5 | 3 | 3.21 | Kept | Nguyen, Phuc | Backend: GET /adherence?patient_id= scoped by consent
3 | 3.24 | PB21 | 1 | 3 | 5 | 3 | 3.22 | Kept | Bao, Duc | Mobile: Family Member adherence view UI
3 | 3.25 | PB21 | 1 | 2 | 3 | 3 | 3.23 | Kept | Viet | Test: adherence history (Family Member)
3 | 3.26 | PB17 | 2 | 3 | 5 | 3 | 3.10 | Kept | Nguyen | Backend: DELETE /links/{id} API
3 | 3.27 | PB17 | 2 | 3 | 5 | 3 | 3.11 | Kept | Bao | Mobile: remove-link UI + confirm dialog
3 | 3.28 | PB18 | 2 | 3 | 5 | 3 | 3.12 | Kept | Viet | Backend: PATCH /links/{id}/consent (shared=false)
3 | 3.29 | PB18 | 2 | 3 | 5 | 3 | 3.13 | Kept | Nguyen | Mobile: toggle data-sharing UI
4 | 4.01 | PB24 | 1 | 9 | 14 | 4 | 4.04 | Kept | Nguyen, Viet | Backend: drug-drug interaction-check logic
4 | 4.02 | PB24 | 1 | 7 | 10.5 | 4 | 4.05 | Kept | Bao, Duc | Mobile: warning screen UI + mandatory disclaimer
4 | 4.03 | PB24 | 1 | 5 | 7 | 4 | 4.06 | Kept | Phuc, Viet | Test: validate interaction-detection algorithm against standardized test-case set (true/false positives) + verify disclaimer always shown
4 | 4.04 | PB25 | 1 | 7 | 10.5 | 4 | 4.07 | Kept | Nguyen, Phuc | Backend: drug-food interaction lookup logic
4 | 4.05 | PB25 | 1 | 5 | 7 | 4 | 4.08 | Kept | Bao, Duc | Mobile: food-warning screen UI (reuse)
4 | 4.06 | PB25 | 1 | 5 | 7 | 4 | 4.09 | Kept | Viet, Phuc | Test: drug-food warning
4 | 4.07 | PB31 | 1 | 9 | 14 | 5 | 5.01 | Moved | Bao, Duc | Research/evaluate ML Kit text recognition on VN packaging samples | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.08 | PB31 | 1 | 12 | 17.5 | 5 | 5.02 | Moved | Duc, Viet | Integrate on-device OCR into mobile app | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.09 | PB31 | 1 | 14 | 21 | 5 | 5.03 | Moved | Nguyen, Viet | Build matching algorithm (OCR text to catalog entry) | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.10 | PB31 | 1 | 9 | 14 | 5 | 5.04 | Moved | Bao, Duc | Build manual-search fallback UI when no match found | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.11 | PB31 | 1 | 5 | 7 | 5 | 5.05 | Moved | Nguyen | Log unmatched items for Admin catalog review | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.12 | PB31 | 1 | 3 | 5 | 5 | 5.06 | Moved | Phuc | Test: OCR accuracy across multiple packaging samples | P1 and highest risk (R-01) pulled earlier, leaves room for P1 in S5
4 | 4.13 | PB07 | 1 | 3 | — | — | — | Added | Duc, Viet | Create Render Web Service from GitHub repo + auto-deploy on push | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
4 | 4.14 | PB07 | 1 | 2 | — | — | — | Added | Viet | Set Render env vars/secrets, prod vs dev config, CORS | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
4 | 4.15 | PB07 | 1 | 5 | — | — | — | Added | Phuc, Duc | Run RQ jobs on Render (Key Value + worker/cron): sync, missed-dose | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
4 | 4.16 | PB07 | 1 | 2 | — | — | — | Added | Viet, Phuc | Check cold-start impact on <2s alert; choose Render plan | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
4 | 4.17 | PB07 | 1 | 3 | — | — | — | Added | Bao, Duc | Point mobile + admin to Render URL; smoke test Android/iOS | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
4 | 4.18 | PB30 | 1 | 7 | 10 | 4 | 4.19 | Kept | Bao, Viet | Cross-device test checklist: onboarding/reminder/confirm (Android)
4 | 4.19 | PB30 | 1 | 7 | 10 | 4 | 4.20 | Kept | Nguyen, Duc | Cross-device test checklist: same flows (iOS)
4 | 4.20 | PB30 | 1 | 3 | 5 | 4 | 4.21 | Kept | Phuc, Bao | Log & triage defects found
5 | 5.01 | PB32 | 1 | 5 | 7.5 | 5 | 5.07 | Kept | Bao, Duc | Mobile: confirmation step showing matched catalog entry | Follows PB31 (S4); confirmation step stays mandatory
5 | 5.02 | PB32 | 1 | 4 | 6.5 | 5 | 5.08 | Kept | Phuc, Viet | Test: confirmation step cannot be skipped | Follows PB31 (S4); confirmation step stays mandatory
5 | 5.03 | PB34 | 1 | 5 | 7.5 | 5 | 5.13 | Kept | Nguyen, Viet | Backend: deletion-request record creation API
5 | 5.04 | PB34 | 1 | 5 | 7.5 | 5 | 5.14 | Kept | Phuc, Bao | Mobile: settings action for withdraw consent / delete data
5 | 5.05 | PB34 | 1 | 4 | 6.5 | 5 | 5.15 | Kept | Phuc, Viet | Test: confirmation shown immediately to patient
5 | 5.06 | PB35 | 1 | 5 | 7.5 | 5 | 5.16 | Kept | Nguyen, Phuc | Backend: Admin queue API for pending requests
5 | 5.07 | PB35 | 1 | 7 | 10 | 5 | 5.17 | Kept | Phuc, Nguyen | Admin dashboard: request queue UI
5 | 5.08 | PB35 | 1 | 3 | 5 | 5 | 5.18 | Kept | Viet | Backend: trigger actual data-deletion job on 'processed'
5 | 5.09 | PB37 | 1 | 12 | 17.5 | 6 | 6.01 | Moved | Nguyen, Viet | Backend: LLM API integration (meal-suggestion prompt + parsing) | P1 pulled earlier; needs PB25 (S4) and the Render env; S6 DPIA update needs the final AI/OCR flows
5 | 5.10 | PB37 | 1 | 5 | 7 | 6 | 6.02 | Moved | Phuc | Backend: mandatory disclaimer injection logic | P1 pulled earlier; needs PB25 (S4) and the Render env; S6 DPIA update needs the final AI/OCR flows
5 | 5.11 | PB37 | 1 | 9 | 14 | 6 | 6.03 | Moved | Bao, Duc | Mobile: meal suggestion UI | P1 pulled earlier; needs PB25 (S4) and the Render env; S6 DPIA update needs the final AI/OCR flows
5 | 5.12 | PB37 | 1 | 3 | 5 | 6 | 6.04 | Moved | Viet | Test: disclaimer always shown, latency acceptable | P1 pulled earlier; needs PB25 (S4) and the Render env; S6 DPIA update needs the final AI/OCR flows
5 | 5.13 | PB22 | 2 | 5 | 7 | 3 | 3.24 | Moved | Phuc | Backend: list linked patients API | P2 pushed later so S3 is P1 first
5 | 5.14 | PB22 | 2 | 12 | 17.5 | 3 | 3.25 | Moved | Bao, Duc | Mobile: patient-switcher UI component | P2 pushed later so S3 is P1 first
5 | 5.15 | PB22 | 2 | 5 | 7 | 3 | 3.26 | Moved | Duc, Viet | Mobile: scope data correctly per selected patient | P2 pushed later so S3 is P1 first
5 | 5.16 | PB22 | 2 | 2 | 3.5 | 3 | 3.27 | Moved | Phuc, Nguyen | Test: verify no cross-patient data leak | P2 pushed later so S3 is P1 first
5 | 5.17 | PB26 | 2 | 3 | 5 | 4 | 4.10 | Moved | Nguyen | Backend: scope lookup API by consent+patient_id | P2 pushed after the P1 items of S4
5 | 5.18 | PB26 | 2 | 3 | 5 | 4 | 4.11 | Moved | Bao | Mobile: Family Member lookup UI | P2 pushed after the P1 items of S4
5 | 5.19 | PB26 | 2 | 2 | 3 | 4 | 4.12 | Moved | Viet | Test: FM lookup scoping | P2 pushed after the P1 items of S4
5 | 5.20 | PB27 | 2 | 5 | 7 | 4 | 4.13 | Moved | Nguyen | Backend: scope drug-drug interaction-check by consent | P2 pushed after the P1 items of S4
5 | 5.21 | PB27 | 2 | 7 | 10.5 | 4 | 4.14 | Moved | Bao, Nguyen | Mobile: FM interaction warning UI (reuse) | P2 pushed after the P1 items of S4
5 | 5.22 | PB27 | 2 | 2 | 3.5 | 4 | 4.15 | Moved | Phuc | Test: FM interaction warning | P2 pushed after the P1 items of S4
5 | 5.23 | PB28 | 2 | 5 | 7 | 4 | 4.16 | Moved | Viet | Backend: scope drug-food interaction by consent | P2 pushed after the P1 items of S4
5 | 5.24 | PB28 | 2 | 5 | 7 | 4 | 4.17 | Moved | Bao, Viet | Mobile: FM food-warning UI (reuse) | P2 pushed after the P1 items of S4
5 | 5.25 | PB28 | 2 | 2 | 3.5 | 4 | 4.18 | Moved | Nguyen | Test: FM food-warning | P2 pushed after the P1 items of S4
6 | 6.01 | PB41 | 1 | 9 | 14 | 6 | 6.08 | Kept | Phuc, Nguyen | Update DPIA with final implemented data flows (AI API + OCR + cross-border assessment), based on S1 preliminary draft
6 | 6.02 | PB41 | 1 | 5 | 7 | 6 | 6.09 | Kept | Phuc | Review DPIA with mentor
6 | 6.03 | PB41 | 1 | 5 | 7 | 6 | 6.10 | Kept | Phuc, Nguyen | Finalize and sign off DPIA
6 | 6.04 | PB33 | 2 | 4 | 6 | 5 | 5.09 | Moved | Bao | Mobile: Simple Mode toggle (persists across sessions) | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.05 | PB33 | 2 | 10 | 15 | 5 | 5.10 | Moved | Bao, Duc | Mobile: simplified screen (next dose + single confirm button) | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.06 | PB33 | 2 | 4 | 6 | 5 | 5.11 | Moved | Duc | Mobile: high-contrast theme + font scaling | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.07 | PB33 | 2 | 3 | 5 | 5 | 5.12 | Moved | Phuc | Test: Simple Mode UX flow | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.08 | PB36 | 2 | 5 | 7.5 | 5 | 5.19 | Moved | Nguyen, Viet | Backend: log entry on every FM/Admin sensitive-data view | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.09 | PB36 | 2 | 5 | 7.5 | 5 | 5.20 | Moved | Phuc, Bao | Admin dashboard: access log viewer UI (filterable) | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.10 | PB36 | 2 | 2 | 3 | 5 | 5.21 | Moved | Viet | Test: log entries created correctly | P2 pushed to the last sprint, can be dropped if S6 slips
6 | 6.11 | PB39 | 2 | 3 | 4 | 6 | 6.05 | Kept | Nguyen, Bao | Backend: scope meal-suggestion by consent+patient_id | Needs PB37 (S5)
6 | 6.12 | PB39 | 2 | 3 | 4 | 6 | 6.06 | Kept | Duc | Mobile: Family Member meal suggestion UI (reuse) | Needs PB37 (S5)
6 | 6.13 | PB39 | 2 | 2 | 3 | 6 | 6.07 | Kept | Bao | Test: FM meal suggestion scoping | Needs PB37 (S5)
6 | 6.14 | PB42 | 1 | 9 | 14 | 6 | 6.11 | Kept | Nguyen, Phuc | Compliance checklist review (all sensitive-data flows)
6 | 6.15 | PB42 | 1 | 7 | 10.5 | 6 | 6.12 | Kept | Nguyen, Viet | Log and resolve any compliance gap found
6 | 6.16 | PB43 | 1 | 14 | 21 | 6 | 6.13 | Kept | Bao, Duc | Retest all Sprint 1-6 features end-to-end | Wording changed: Sprint 1-5 -> 1-6 (S6 now also holds PB33/PB36)
6 | 6.17 | PB43 | 1 | 18 | 28 | 6 | 6.14 | Kept | Bao, Duc, Viet | Fix Critical/High severity bugs
6 | 6.18 | PB43 | 1 | 9 | 14 | 6 | 6.15 | Kept | Duc, Bao | Fix Medium/Low severity bugs (time permitting)
6 | 6.19 | PB43 | 1 | 5 | 7 | 6 | 6.16 | Kept | Viet, Phuc | Final regression test before Integration phase
6 | 6.20 | PB07 | 1 | 3 | — | — | — | Added | Duc, Viet | Final Render redeploy: prod env (LLM key) + deployment runbook | New: Render deployment (S4 deploy + smoke test; S6 final redeploy + runbook)
— | — | PB07 | 1 | — | 10 | 1 | 1.04 | Removed | Bao | Setup GitHub Actions (lint + test on PR) | Dropped: GitHub Actions / Oracle Cloud VM / Caddy no longer used (backend moves to Render)
— | — | PB07 | 1 | — | 10 | 1 | 1.05 | Removed | Duc | Setup auto-deploy to Oracle Cloud VM | Dropped: GitHub Actions / Oracle Cloud VM / Caddy no longer used (backend moves to Render)
— | — | PB07 | 1 | — | 7 | 1 | 1.06 | Removed | Viet | Configure Caddy for automatic HTTPS | Dropped: GitHub Actions / Oracle Cloud VM / Caddy no longer used (backend moves to Render)