## Gantt Chart
DrugTime - Project Master Gantt Chart
PROJECT: DrugTime MVP - Mobile Medication Management Platform |  | SPONSOR: International School, Duy Tan University |  | TIMELINE: 9/10/2026 to 12/25/2026 (16 Weeks)
PROJECT LEAD: Phuc Nguyen Ngoc ¦ MENTOR: Giap Trong Nguyen (Kaopiz Da Nang) |  | TEAM: Nguyen Ngoc Phuc, Nguyen Quang Bao, Nguyen Tan Duc, Nguyen Van Nguyen, Dang Ngo Ngoc Viet |  | SPRINT CYCLE: 6 Sprints x 2 Weeks (14 Days)
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | % OF TASK COMPLETE | PHASE 1: INITIATION & ARCHITECTURE DESIGN | [9 empty] | PHASE 2: IMPLEMENTATION (SPRINT 1 TO SPRINT 6) | [54 empty] | PHASE 3: INTEGRATION, FINAL RELEASE & DEFENSE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | SEPTEMBER 2026 | [17 empty] | OCTOBER 2026 | [21 empty] | NOVEMBER 2026 | [20 empty] | DECEMBER 2026
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[7 empty] | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25
1 | Project Initiation & Stakeholder Alignment |  | 9/10 | 9/13 | 3 | 100% | bar: SEPTEMBER 2026 R 10 to SEPTEMBER 2026 F 11
1.1 | Requirement Gathering & Stakeholder Needs (Patients/Caregivers/Pharmacies) | Team 1 | 9/10 | 9/11 | 2 | 100% | bar: SEPTEMBER 2026 R 10 to SEPTEMBER 2026 F 11
1.2 | Project Proposal Preparation & Cost/Budget Estimation ($3,998) | Team 0 | 9/11 | 9/12 | 2 | 100% | bar: SEPTEMBER 2026 F 11
1.3 | Proposal Presentation & Capstone Review Panel Approval | Team 1 | 9/12 | 9/13 | 2 | 100%
2 | Planning & Architecture Design |  | 9/12 | 9/25 | 13 | 100% | bar: SEPTEMBER 2026 M 14 to SEPTEMBER 2026 F 25
2.1 | Project Plan Preparation, Work Breakdown & Risk Register | Nguyen Ngoc Phuc | 9/12 | 9/14 | 3 | 100% | bar: SEPTEMBER 2026 M 14
2.2 | Architecture Design Document (Context/Container/Component & Non-functional) | Duc, Bao, Viet | 9/14 | 9/18 | 5 | 100% | bar: SEPTEMBER 2026 M 14 to SEPTEMBER 2026 F 18
2.3 | Database Design Documents & Entity-Relationship Specifications (Schema v2) | Phuc, Nguyen | 9/21 | 9/25 | 5 | 100% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 F 25
3 | Sprint 1 - Platform, Identity & Core Data |  | 9/14 | 9/27 | 14 | 35% | bar: SEPTEMBER 2026 M 14 to SEPTEMBER 2026 F 25
3.01 | [1.01] PB08: Design ERD (patient, medication, consent, catalog tables) |  | 9/14 | 9/16 | 3 | 100% | bar: SEPTEMBER 2026 M 14 to SEPTEMBER 2026 W 16
3.02 | [1.02] PB08: Write Supabase migration scripts |  | 9/16 | 9/18 | 3 | 0% | bar: SEPTEMBER 2026 W 16 to SEPTEMBER 2026 F 18
3.03 | [1.03] PB08: Review & test migrations on clean DB |  | 9/18 | 9/21 | 2 | 0% | bar: SEPTEMBER 2026 F 18 to SEPTEMBER 2026 M 21
3.04 | [1.04] PB07: Setup GitHub Actions (lint + test on PR) |  | 9/14 | 9/17 | 4 | 0% | bar: SEPTEMBER 2026 M 14 to SEPTEMBER 2026 R 17
3.05 | [1.05] PB07: Setup auto-deploy to Oracle Cloud VM & Caddy reverse proxy |  | 9/17 | 9/21 | 3 | 0% | bar: SEPTEMBER 2026 R 17 to SEPTEMBER 2026 M 21
3.06 | [1.07] PB29: Confirm Mac access + configure free Apple ID in Xcode |  | 9/18 | 9/21 | 2 | 0% | bar: SEPTEMBER 2026 F 18 to SEPTEMBER 2026 M 21
3.07 | [1.08] PB29: Configure Xcode project + automatic signing |  | 9/21 | 9/23 | 3 | 0% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 W 23
3.08 | [1.09] PB29: Test: build & run app on real device via Xcode (debugging) |  | 9/23 | 9/25 | 3 | 0% | bar: SEPTEMBER 2026 W 23 to SEPTEMBER 2026 F 25
3.09 | [1.10] PB01: Backend: Supabase Auth integration (register/login API) |  | 9/21 | 9/23 | 3 | 0% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 W 23
3.10 | [1.11] PB01: Mobile: Register/Login UI screens (Flutter) |  | 9/21 | 9/24 | 4 | 0% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 R 24
3.11 | [1.12] PB01: Mobile-Backend integration + error handling |  | 9/24 | 9/25 | 2 | 0% | bar: SEPTEMBER 2026 R 24 to SEPTEMBER 2026 F 25
3.12 | [1.13] PB01: Test: unit + widget test (Auth flow) |  | 9/25 | 9/25 | 1 | 0% | bar: SEPTEMBER 2026 F 25
3.13 | [1.14] PB02: Backend: consents table + grant/revoke API per purpose (PDPL 2025) |  | 9/21 | 9/23 | 3 | 0% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 W 23
3.14 | [1.15] PB02: Mobile: consent UI (per-purpose toggles, no 'Accept All') |  | 9/23 | 9/25 | 3 | 0% | bar: SEPTEMBER 2026 W 23 to SEPTEMBER 2026 F 25
3.15 | [1.16] PB02: Test: consent flow end-to-end |  | 9/25 | 9/25 | 1 | 0% | bar: SEPTEMBER 2026 F 25
3.16 | [1.17] PB06: Research/parse Vietnamese Drug Regulatory Data Source structure |  | 9/15 | 9/22 | 6 | 0% | bar: SEPTEMBER 2026 T 15 to SEPTEMBER 2026 T 22
3.17 | [1.18] PB06: Build RQ scheduled sync job & Redis queue |  | 9/21 | 9/25 | 5 | 0% | bar: SEPTEMBER 2026 M 21 to SEPTEMBER 2026 F 25
3.18 | [1.19] PB41: Draft preliminary DPIA (planned sensitive-data flows) |  | 9/22 | 9/25 | 4 | 0% | bar: SEPTEMBER 2026 T 22 to SEPTEMBER 2026 F 25
4 | Sprint 2 - Core Reminders & Schedules |  | 9/28 | 10/11 | 14 | 0% | bar: SEPTEMBER 2026 M 28 to OCTOBER 2026 F 9
4.1 | [PB10] Medication Entry API & Mobile Manual Form |  | 9/28 | 10/2 | 5 | 0% | bar: SEPTEMBER 2026 M 28 to OCTOBER 2026 F 2
4.2 | [PB11] Medication Schedule CRUD API & Edit UI |  | 10/1 | 10/6 | 4 | 0% | bar: OCTOBER 2026 R 1 to OCTOBER 2026 T 6
4.3 | [PB12] Local Notification Engine & Offline Reminder Scheduling |  | 10/5 | 10/9 | 5 | 0% | bar: OCTOBER 2026 M 5 to OCTOBER 2026 F 9
4.4 | [PB13] Dose Confirmation Intake Button & Logging |  | 10/7 | 10/9 | 3 | 0% | bar: OCTOBER 2026 W 7 to OCTOBER 2026 F 9
4.5 | [PB04/05] Admin Web Dashboard: Medication & Interaction Catalog CRUD |  | 9/28 | 10/8 | 9 | 0% | bar: SEPTEMBER 2026 M 28 to OCTOBER 2026 R 8
4.6 | [PB09] Patient-Family Linking Data Model & Migration |  | 10/5 | 10/9 | 5 | 0% | bar: OCTOBER 2026 M 5 to OCTOBER 2026 F 9
5 | Sprint 3 - Adherence Tracking & Family Connection |  | 10/12 | 10/25 | 14 | 0% | bar: OCTOBER 2026 M 12 to OCTOBER 2026 F 23
5.1 | [PB14] Adherence History Calendar & Summary View |  | 10/12 | 10/16 | 5 | 0% | bar: OCTOBER 2026 M 12 to OCTOBER 2026 F 16
5.2 | [PB15/19] QR Code & Referral Code Linking Mechanism |  | 10/14 | 10/19 | 4 | 0% | bar: OCTOBER 2026 W 14 to OCTOBER 2026 M 19
5.3 | [PB16/18] Data-Sharing Consent Controls & Scoped Revocation |  | 10/16 | 10/21 | 4 | 0% | bar: OCTOBER 2026 F 16 to OCTOBER 2026 W 21
5.4 | [PB20] Real-time Missed-Dose Alerts for Linked Caregivers |  | 10/19 | 10/23 | 5 | 0% | bar: OCTOBER 2026 M 19 to OCTOBER 2026 F 23
5.5 | [PB22] Multi-Patient Switcher UI for Family Caregivers |  | 10/21 | 10/23 | 3 | 0% | bar: OCTOBER 2026 W 21 to OCTOBER 2026 F 23
6 | Sprint 4 - Medical Safety & Drug Lookup |  | 10/26 | 11/8 | 14 | 0% | bar: OCTOBER 2026 M 26 to NOVEMBER 2026 F 6
6.1 | [PB23] Vietnamese Drug Regulatory Catalog Search & Detail View |  | 10/26 | 10/30 | 5 | 0% | bar: OCTOBER 2026 M 26 to OCTOBER 2026 F 30
6.2 | [PB24] Drug-Drug Interaction Checking Engine & Warning UI |  | 10/28 | 11/3 | 5 | 0% | bar: OCTOBER 2026 W 28 to NOVEMBER 2026 T 3
6.3 | [PB25] Drug-Food Interaction Checking Engine & Warning UI |  | 11/2 | 11/6 | 5 | 0% | bar: NOVEMBER 2026 M 2 to NOVEMBER 2026 F 6
6.4 | [PB26-28] Family Member Scoped Access for Drug Safety Lookup |  | 11/4 | 11/6 | 3 | 0% | bar: NOVEMBER 2026 W 4 to NOVEMBER 2026 F 6
6.5 | [PB30] Cross-Device Android & iOS Comprehensive Testing Checklist |  | 11/5 | 11/6 | 2 | 0% | bar: NOVEMBER 2026 R 5 to NOVEMBER 2026 F 6
7 | Sprint 5 - High-Risk / Complex Features |  | 11/9 | 11/22 | 14 | 0% | bar: NOVEMBER 2026 M 9 to NOVEMBER 2026 F 20
7.1 | [PB31] On-Device ML Kit OCR for Blister-Pack Scanning |  | 11/9 | 11/13 | 5 | 0% | bar: NOVEMBER 2026 M 9 to NOVEMBER 2026 F 13
7.2 | [PB32] OCR Text Matching Algorithm & Mandatory Manual Confirmation |  | 11/12 | 11/17 | 4 | 0% | bar: NOVEMBER 2026 R 12 to NOVEMBER 2026 T 17
7.3 | [PB33] Simple Mode High-Contrast UI for Elderly Users |  | 11/16 | 11/19 | 4 | 0% | bar: NOVEMBER 2026 M 16 to NOVEMBER 2026 R 19
7.4 | [PB34/35] Consent Withdrawal & Right-to-be-Forgotten Data Deletion Flow |  | 11/16 | 11/20 | 5 | 0% | bar: NOVEMBER 2026 M 16 to NOVEMBER 2026 F 20
7.5 | [PB36] Sensitive-Data Access Audit Logging & Admin Log Viewer |  | 11/18 | 11/20 | 3 | 0% | bar: NOVEMBER 2026 W 18 to NOVEMBER 2026 F 20
8 | Sprint 6 - AI & Final Polish |  | 11/23 | 12/6 | 14 | 0% | bar: NOVEMBER 2026 M 23 to DECEMBER 2026 F 4
8.1 | [PB37] AI Meal Suggestion Engine with Explanations & Medical Disclaimers |  | 11/23 | 11/27 | 5 | 0% | bar: NOVEMBER 2026 M 23 to NOVEMBER 2026 F 27
8.2 | [PB39] Scoped AI Meal Suggestions for Family Caregivers |  | 11/26 | 11/30 | 3 | 0% | bar: NOVEMBER 2026 R 26 to NOVEMBER 2026 M 30
8.3 | [PB41/42] Final DPIA Sign-Off & PDPL 2025 Regulatory Compliance Audit |  | 11/26 | 12/1 | 4 | 0% | bar: NOVEMBER 2026 R 26 to DECEMBER 2026 T 1
8.4 | [PB43] Full-System Regression Testing & Defect Fixing (Android + iOS) |  | 11/30 | 12/4 | 5 | 0% | bar: NOVEMBER 2026 M 30 to DECEMBER 2026 F 4
9 | Integration and Final Release |  | 12/7 | 12/16 | 10 | 0% | bar: DECEMBER 2026 M 7 to DECEMBER 2026 W 16
9.1 | End-to-End Core User Journey Verification (Onboard -> Reminder -> Dose -> Alert -> AI) |  | 12/7 | 12/9 | 3 | 0% | bar: DECEMBER 2026 M 7 to DECEMBER 2026 W 9
9.2 | Final Submission Package (Source Code, APK/IPA, Docs, Deployment Setup) |  | 12/10 | 12/14 | 3 | 0% | bar: DECEMBER 2026 R 10 to DECEMBER 2026 M 14
9.3 | Project Retrospective & Capstone Defense Demo Rehearsal |  | 12/14 | 12/16 | 3 | 0% | bar: DECEMBER 2026 M 14 to DECEMBER 2026 W 16
10 | Capstone Defense |  | 12/17 | 12/25 | 7 | 0% | bar: DECEMBER 2026 R 17 to DECEMBER 2026 F 25
10.1 | Capstone Project 1 Final Defense Presentation & System Demonstration |  | 12/17 | 12/25 | 7 | 0% | bar: DECEMBER 2026 R 17 to DECEMBER 2026 F 25