DrugTime

Project Charter

Septembeer 21st

Document Status: Draft | In Review | Approved

Executive Summary:

DrugTime is a mobile-first medication management platform for Vietnamese patients, especially elderly and chronic-disease patients managing multiple medications. Focusing on medication entry, local reminders, dose confirmation, Vietnamese drug-interaction lookup, family caregiver monitoring, Simple Mode, AI-assisted meal suggestions, and consent-driven data protection for Android and iOS.

Project Goal

SMART project goal: - Deliver and validate the Phase 1 DrugTime MVP for Android and iOS within the project schedule. - Complete the six planned two-week development sprints from 14-Sep-2026 to 06-Dec-2026. - Complete system integration, final submission, and defense preparation by 16-Dec-2026. - Meet the defined non-functional targets for normal-load response time (≤ 2 seconds for reminder/dose-confirmation actions) and core-service availability (≥ 99%). - Implement purpose-separated consent, consent withdrawal/deletion mechanisms, sensitive-data access logging, and the planned DPIA/compliance activities.

Deliverables

- Project Plan and risk register. - Architecture Design Document, including context/container/component views. - Database Design Document. - Flutter Android/iOS MVP with medication management, reminders, adherence tracking, family linking, drug-safety lookup, Simple Mode, blister-pack scanning, and AI meal suggestions. - React + Next.js Admin dashboard for catalogue and compliance operations. - FastAPI modular-monolith backend with RQ/Redis background jobs and Supabase data storage. - DPIA/compliance checklist and purpose-separated consent, withdrawal/deletion, and audit-log mechanisms. - 8. Integrated system, final source code/documentation/deployment package, and capstone defense materials.

Business Case / Background

Why are we doing this? - The proposal reports that 75% of 60 surveyed respondents in Da Nang had forgotten a medication in the previous week, while only 5% used a dedicated medication-reminder app. - Vietnamese patients using multiple medications need a localized way to manage schedules and access interaction information aligned with Vietnamese drug references. - Families need a real-time view of missed doses and adherence history when the patient explicitly grants access. - DrugTime is intended to bridge gaps identified in the proposal by combining medication reminders, Vietnamese-formulary drug-safety lookup, family monitoring, and AI-assisted meal suggestions in one consent-driven platform. - The project is also intended to demonstrate responsible handling of sensitive health data through purpose-separated consent, access control, deletion/withdrawal flows, and audit logging. The Plant Pals can run smoothly with a high-quality customer experience and supports the larger project goal of a 5% revenue increase for Office Green

Benefits, Costs, and Budget

Benefits: - Support medication adherence through scheduled reminders and dose confirmation - Give patients access to Vietnamese-localized drug and interaction information with medical disclaimers. - Allow family caregivers to receive missed-dose alerts and view adherence history when authorized. - Provide a Simple Mode for users with lower technology literacy. - Establish a foundation that can be extended with Phase 2 capabilities after MVP validation. Costs: - Estimated project cost in the proposal: $3,998. - Main cost components: 1,750 working hours at USD 2/hour, AI tools at USD 198, and USD 300 contingency. - The proposal also identifies the Apple Developer Program (USD 99/year) as required for the in-scope iOS build. Budget needed: - $3,998

Scope and Exclusion

In-Scope (Phase 1 MVP): - User registration/login and purpose-separated consent. - Manual medication entry and on-device blister-pack scanning with mandatory manual verification. - Local medication reminders, dose confirmation, and adherence history. - Vietnamese drug lookup and drug-drug/drug-food interaction warnings with medical disclaimers. - AI-based meal suggestions with explanations and disclaimers. - Simple Mode with simplified, high-contrast UI. - Family linking, missed-dose alerts, adherence monitoring, and multi-patient access under explicit consent. - Admin medication/interaction catalogue management, synchronization, DPIA/compliance operations, deletion/withdrawal processing, and sensitive-data access logs. - Android and iOS MVP, plus Admin web dashboard. Out-of-Scope (Phase 2): - Prescription OCR. - Partner-pharmacy QR/barcode integrations. - Zalo OA reminders. - Voice-based dose confirmation. - Pharmacist consultation / Ask-a-pharmacist escalation. - Partner-pharmacy promotions map and data sharing. - Refill reminders and wearable-device integration. - Medication usage guide and Premium subscription.

Project Team

Project Sponsor: International School, Duy Tan University Project Mentor: Giap Trong Nguyen, Kaopiz Da Nang Project Lead: Phuc Nguyen Ngoc Project Team: - Nguyen Ngoc Phuc — Leader, Dev, QA - Nguyen Quang Bao — Dev, QA, DevOps - Nguyen Tan Duc — Dev, QA, DevOps - Nguyen Van Nguyen — BA, Dev, QA - Dang Ngo Ngoc Viet — Dev, QA, DevOps Additional Stakeholders: Patients (primary users), Family members/caregivers, Admin, Partner pharmacy staff and partner pharmacists (Phase 2), Capstone review panel / mentor

Measuring Success

What is acceptable: - Phase 1 MVP scope is implemented and demonstrated for Android and iOS according to the approved proposal. - The six planned sprints are completed by 06-Dec-2026, followed by integration and release activities through 16-Dec-2026. - Final submission package is completed by 13-Dec-2026 and defense preparation is completed by 16-Dec-2026. - Reminder notifications and dose-confirmation actions meet the stated ≤ 2-second target under normal load. - Core services meet the stated ≥ 99% availability target. - Purpose-separated consent, withdrawal/deletion flows, sensitive-data access logging, and the planned compliance/DPIA activities are implemented as specified. - 7. Core end-to-end scenario passes: onboarding → reminder → confirmation → family alert → interaction lookup → AI meal suggestion.